Project Resourcing & Schedule

Management System

Quarterly PRSM Status Report to the Legislature

March 1, 2010 – May 28, 2010

California Department of Transportation

Division of Project Management

Office of Statewide Project Management Improvement

Table of Contents

Independent Project Oversight Reports	1

IPO Report for May 2010	1

Project Oversight Review Checklist for May 2010	9

IPO Report for April 2010	14

Project Oversight Review Checklist for April 2010	21

IPO Report for March 2010	27

Project Oversight Review Checklist for March 2010	34

# Independent Project Oversight Reports

## IPO Report for May 2010

| Project Name: | Caltrans PRSM | Assessment Date: | May 28, 2010 |
| --- | --- | --- | --- |
|  | Frequency: |  |

Oversight Provider Information

| Oversight Leader: | Greg Thomas | Organization: | Deloitte & Touche LLP |
| --- | --- | --- | --- |
| Phone Number: | 415 783 5211 | Email: | grethomas@deloitte.com |

Project Information

| Project Number: | 2660-160 | Department: | Transportation (Caltrans) |
| --- | --- | --- | --- |
| Criticality: | High | Agency: | Business, Transportation & Housing |
| Last Approved Document/Date: | SPR (12/08/09) | Total One-time Cost: | $26,078,375 |
| Start Date: | June 7, 2000 | End Date: | June 13, 2011 |
| Project Manager: | David Youmans | Organization: | Caltrans |
| Phone Number: | 916.826.4425 | Email: | david_youmans@dot.ca.gov |

Summary: Current Status

| Project Phase: | Adaptation |
| --- | --- |
| Planned Start Date: | May 20, 2009 | Planned End Date: | February 2, 2010 |
| Actual Start Date: | July 1, 2009 | Forecasted End Date: June 29, 2010 |

Schedule

Select the statement that most closely applies, measured against the last Finance approved document.

| Behind Schedule | Ahead-of-schedule: One or more major tasks or milestones have been completed and approved early (> 5%). All other major tasks and milestones completed and approved according to plan. On-schedule: All major tasks and milestones have been completed and approved according to plan. (Within 5%) Behind Schedule: One or more major tasks or milestones are expected to be delayed. (> 5%) |
| --- | --- |
| Comments: | A new baseline schedule was set with the approved Special Project Report (SPR) dated December 8, 2009. The SPR states the end date of the Adaptation Phase as February 2010 and the end date of the entire PRSM project as June 13, 2011. According to the last approved project schedule (presented during the March 2, 2010 PRSM Project status meeting), the Implementation Vendor identified the Adaptation Phase completion date as June 29, 2010 and the PRSM project completion date as October 10, 2011. This represents a difference of four (4) months or approximately a 57% delay for the Adaptation Phase and an extension of the project by four (4) months or approximately a 15% delay. Given this change, IPOC has reported the project as “Behind Schedule”. In the April 2010 reporting period, the Implementation Vendor re-evaluated the PRSM project schedule and submitted a revised draft schedule. Since April, the proposed schedule has gone through additional revisions, which resulted in additional delays. The most recent draft schedule (presented during the May 25, 2010 PRSM Project status meeting), reflects an approximate five (5) month delay from the last approved project schedule for both the Adaptation Phase and the project completion date. Please refer to the table below for additional information. The PRSM project team is currently in the process of reviewing the revised draft schedule and identifying the root causes of the delay. Please note that while the Draft schedule is showing additional delays, efforts by the PRSM Project Team (such as concurrent configuration of agreed upon requirements) are currently underway to offset some of the delay in Adaptation. We will continue to closely monitor the schedule status during the Adaptation Phase and report any updates as they occur. Please refer to the PRSM Project Schedule issue in the Issue section below for information regarding further potential impacts to the schedule. Document End of Adaptation Phase End of Project SPR (dated 12/08/09) 02/2010 06/13/2011 Last Approved Schedule (dated 03/02/2010) 06/29/2010 10/10/2011 Draft Proposed Schedule (dated 05/25/2010) 12/2/2010 03/12/2012 |

Resources (Level of Effort) Choose the statement that most closely applies.

| Within Resources | Fewer Resources Completion of one or more major tasks and/or acceptable products has required or is expected to require materially (>5%) fewer hours/staff than planned. Within Resources All major tasks have been completed and acceptable products created using the planned number of hours/staff (within 5%). More Resources Completion of major tasks and/or acceptable products has required or is expected to require materially (>5%) more hours/staff than planned. |
| --- | --- |
| Comments: | A new baseline was set with the approved SPR dated 12/08/2009. |

Resources (Budget/Cost) Choose the statement that most closely applies.

| Within Cost | Less cost The project is (>5%) under budget. Within cost The project is operating within budget. Higher cost Material budget increases (>5%) are likely. |
| --- | --- |
| Comments: | A new baseline was set with the approved SPR dated 12/08/2009. Please refer to the PRSM Project Cost Increase risk in the New Risks section below for information regarding potential impacts to project costs. |

Quality (Client Functionality) Choose the statement that most closely applies.

| Inadequately Defined | Adequately Defined Required client functionality is adequately defined, and is being successfully built into the system, given the current project phase. Inadequately Defined One or more significant components of required client functionality are inadequately defined, or are not being successfully built into the system, given the current project phase. |
| --- | --- |
| Comments: | Client functionality (scope) is not adequately defined for the Adaptation Phase which began on July 1, 2009. In the April 2010 reporting period, the Implementation Vendor re-evaluated the PRSM project schedule and submitted a revised draft schedule. Since April, the proposed schedule has gone through additional revisions, which resulted in additional delays. The most recent draft schedule (presented during the May 25, 2010 PRSM Project status meeting), reflects an approximate five (5) month delay from the last approved project schedule for both the Adaptation Phase and the project completion date. Please refer to the Schedule section above for additional information. Through inspection of the revised draft schedule, it was noted that one of the items which may have impacted the delay in Adaptation is the Requirements Baselining effort, which includes the analysis and approval of Project Change Request’s (PCR’s) 8, 9, and 12. Please note that PCR’s 8, 9, and 12 are currently open and represent changes and/or deletions to existing requirements / functionality. The majority of these changes involve interface requirements. In addition, another area which may have impacted the delay in Adaptation is the ERP Financial Infrastructure (EFIS) Interface development effort. The PRSM Project Team has been made aware that Caltrans Financial Data to Oracle (FIDO) system and Earned Value Reporting System (EVRS) are going to be phased out once the EFIS has been implemented. Based on this information, the PRSM Project Team has created PCR 13, which involves building an interface to EFIS. Per the draft schedule presented during the May 25, 2010 PRSM Project status meeting, the Requirements Baselining effort is scheduled to be completed on June 16, 2010. The PRSM Project Team is working with the Implementation Vendor to close out PCR’s 8, 9, 12, and 13. Once this effort has been completed and PCR’s 8, 9, 12, and 13 are closed, functionality should be adequately defined for the Adaptation Phase. Please refer to the “Project Change Requests Finalization and Approval” risk in the Risks section below for information regarding further potential impacts to the schedule. In addition to the open PCR’s, another area which may have had an impact on the delay in Adaptation is the uncertainty around the percent complete for configuration. The PRSM Project Team has been monitoring the following risk (Risk #80 on the PRSM Risk Log) identified by the IV&V Vendor: Clarity configuration checkpoints have not been effective at measuring project progress. A requirements traceability matrix showing the configuration status of each requirement has not been produced. It is unclear how many of the configurations have been completed and if the configurations are on schedule. The PRSM Project Team is currently having discussions with the Implementation Vendor to determine the percentage of configuration that has been completed at this stage. We will continue to closely monitor the functionality status during the Adaptation Phase and report any updates as they occur. |

Quality (Architecture/System Performance) Choose the statement that most closely applies.

|  | Adequately Defined The system technical architecture is adequately defined, and modeling, benchmarking and testing are being conducted (or are planned) appropriate to the current project phase. Inadequately Defined The system technical architecture is not adequately defined, or modeling, benchmarking and testing are not being conducted (or are planned) appropriate to the current project phase. |
| --- | --- |
| Comments: | System technical architecture and performance are adequately defined for the Adaptation Phase. The Implementation Vendor has submitted a Configuration Management Plan, High Level Design, and updated Architecture Diagram. The Production environment hardware has been configured and turned over to Caltrans. |

Issues

Issue I-1: PRSM Project Schedule

Issue Statement: In the April 2010 reporting period, the Implementation Vendor re-evaluated the PRSM project schedule and submitted a revised draft schedule.  Since April, the proposed schedule has gone through additional revisions.  The most recent draft schedule (presented during the May 25, 2010 PRSM Project status meeting), reflects an approximate five (5) month delay from the last approved project schedule for both the Adaptation Phase and the project completion date.  At this point in time, the Caltrans PRSM Project team and the Implementation Vendor are not in agreement with the dates in the revised draft schedule.

Impact: High	Time Frame:  Short Term	Severity:  High	Assigned to: David Youmans

IPOC Recommendations:

- I-1a - IPOC recommends that the revised draft schedule is vetted with the PRSM Project Team, the Implementation Vendor, and Project Stakeholders and a consensus/agreement on the finalized schedule is completed by the end of the next reporting period (June 2010).

- I-1b - In addition to the resolution of the PRSM Project Schedule, any cost impact associated with the additional delays in the schedule should be determined by the end of the next reporting period (June 2010).  Please refer to the PRSM Project Cost Increase risk in the New Risks section below for information regarding potential impacts to project costs

Status Update:

May 10 Status:	As of the end of this reporting period, Caltrans and the Implementation Vendor have not come to an agreement regarding the updated draft schedule proposed by the Implementation Vendor.  Although this schedule has not gone through change management and been approved, during the month of May, the PRSM Project Team was utilizing the draft schedule to monitor and track the status of the project during status meetings.  This is due to the fact that the last approved project schedule (presented during the March 2, 2010 PRSM Project status meeting) currently does not reflect PRSM task and milestone dates accurately.

Issue I-2: EFIS Interface

Issue Statement: The PRSM Project Team has been made aware that Caltrans Financial Data to Oracle (FIDO) system and Earned Value Reporting System (EVRS) are going to be phased out once the ERP Financial Infrastructure (EFIS) has been implemented.  While developing to one standard interface presents a business opportunity, specifications and data requirements will need to be analyzed and documented.  The development of the EFIS interface is a critical step for the PRSM project to proceed to the Pilot phase.  Currently EFIS is scheduled to go-live in July 2010 and PRSM is scheduled to begin Pilot on 6/28/2010.  A delay in the EFIS schedule could significantly delay the PRSM pilot and roll out to the Districts.   In addition, the development of the EFIS interface could impact the cost of PRSM.  There are three (3) potential scenarios related to this issue that could impact the schedule and/or cost: 1) a delay in the EFIS project could result in a delay to PRSM; 2) the complexity of the interface to EFIS and the activities/tasks involved could result in a delay to PRSM and/or impact cost; and 3) a delay in the EFIS training schedule could conflict with the PRSM training schedule, which could result in a delay to PRSM.

Impact: High	Time Frame:  Short Term	Severity:  High	Assigned to: Jacqueline Moore

IPOC Recommendations:

- I-2a - Develop a detailed action plan for the EFIS interface that addresses the following: impact to the data conversion effort, impact to districts and end users, impact to project resources, impact to schedule, and impact to costs.

- I-2b - Update the PRSM project schedule with the activities associated with the EFIS interface, including analysis activities.

- I-2c - Continue to work closely with the EFIS project by attending the bi-weekly interface planning meetings.  Escalate issues related to EFIS timing and resource needs to the PRSM Steering Committee for resolution as soon as the interface requirements are finalized.

Status Update:

May 10 Status:	No new status

April 10 Status:	Per the draft schedule presented during the April 27, 2010 PRSM Project status meeting, EFIS data conversion activities are scheduled to be completed in June 2010.  In addition, the EFIS Development effort (including Integration Testing) is scheduled to be completed in September 2010.  An impact analysis is currently being performed for the EFIS interface change request (PCR 13).  The PRSM Project Team continues to meet with the EFIS Project Team on a weekly basis.  In addition three (3) EFIS risks have been added to the PRSM Risk Log, risks 76A, 76B, and 77.  These risks are discussed during the monthly PRSM Risk Management meeting.

New Risks

*New Risk R-6: PRSM Project Cost Increase

Risk Statement: The delays in the PRSM project schedule and the uncertainty in approving the Project Change Request’s could have an impact on the cost of the project.  Based on the draft schedule proposed by the Implementation Vendor, it is likely the Implementation Vendor will submit a change request for increased costs.

Probability:  High        Impact: High     Time Frame:  Short Term	   Severity:  High	       Assigned to: David Youmans

Recommendation:

- R-6a - IPOC recommends that any cost impact associated with the delays in the schedule should be identified and communicated to PRSM project stakeholders by the end of the next reporting period (June 2010).

Progress Toward Addressing Prior Risks

RiskR-5: Project Change Requests Finalization and Approval

Risk Statement: The delay and uncertainty in approving Project Change Request’s 8,9,12, and 13 could have further impact on the schedule and cost of the project.

Probability:  High        Impact: High     Time Frame:  Short Term	   Severity:  High	       Assigned to: David Youmans

Recommendation:

- R-5a - IPOC recommends that PCR 8, 9, 12, and 13 are clarified and approved by the end of the next reporting period (June 2010).

Status Update:

May 10 Status:	PCR’s 8, 9, 12, and 13 remain open as of the end of this reporting period

Risk R-4: PRSM Task Dependency Identification

Risk Statement: Recent activities to refresh/reevaluate the schedule have resulted in a significant number of previous unknown dependencies between interface development activities, configuration activities, and data conversion activities.  The identification of these could result in further delay to the overall project schedule.

Probability:  High        Impact: High     Time Frame:  Long Term	   Severity:  High	       Assigned to: David Youmans

Recommendation:

- R-4a - During the weekly PRSM Project Status meetings, IPOC recommends that each of the Caltrans PRSM Project Team Workgroups conduct brief and more frequent status meetings regarding status of tasks, dependencies, risks and issues associated with those tasks.  In addition, IPOC recommends that the PRSM Project Team continues to refine the schedule for project phases after Adaptation to ensure that any risk of further schedule slippage is mitigated and so that the total impact of known dependencies on the schedule can be understood and communicated to stakeholders.

Status Update:

May 10 Status:	No new status

April 10 Status:	The PRSM Project Team has continued to reevaluate the PRSM Project Schedule during the month of December.  During the weekly PRSM Project Status meetings, current and up-coming tasks are discussed and risks and dependencies associated with those tasks are identified.  For a status update on the requirements baselining process, please refer to Risk: Business Rules and Business Process Changes below.

Risk R-3: PRSM Project Team Communications

Risk Statement: Effective, clear and frequent communications between the Caltrans PRSM team, the Implementation Vendor, other vendors (e.g., testing and data conversion), and District stakeholder is critical given the size and complexity of PRSM during the Adaptation Phase.  The new Communications Plan, while documented, needs to be fully implemented early in the Adaptation Phase.  Without effective communications, the PRSM project schedule, scope and quality could be difficult to manage and control.

Probability:  Medium        Impact: High     Time Frame:  Long Term	   Severity:  High	       Assigned to: David Youmans

IPOC Recommendations:

- R-3a - In addition to the weekly PRSM Project Status meetings, IPOC recommends that Caltrans PRSM Project Management and Implementation Vendor Project Management conduct frequent status meetings in order to discuss the status of high priority issues and action items.  These checkpoint meetings should be no longer than ½ hour in duration and conducted twice per week (i.e., Monday AM and Thursday PM).

- R-3b - Expedite the communication of the detailed To-Be Business Process changes to the Districts so that they can gain a better understanding of the impacts and benefits of PRSM.

Status Update:

May 10 Status:	Beginning in May 2010, PRSM project status meetings have begun occurring on a bi-weekly basis versus a weekly basis.  In addition, a task has been added to the meeting agenda to discuss the status of the previous meetings action items and to identify new action items.

April 10 Status:	Beginning in January 2010, project risks have been added as a discussion point during the weekly PRSM project status meetings.  During this discussion, a select number of risks are discussed, including their current status, impact, and remediation steps.  The Communications Plan was formally approved in the month of August and provides details surrounding the methods of communication for the PRSM project.  PRSM Project Status meetings continue to occur on a weekly basis.  PRSM sub-teams meet at a minimum of once a week to discuss current and upcoming tasks.  In addition to the PRSM Project Team meetings, Caltrans prepares and distributes a monthly newsletter and “Nuggets of Knowledge” memo to the districts.  Implementation Team training sessions have been scheduled during the month of September that will provide the PRSM Implementation Team with an overview of PRSM Methodology and Functionality.  Previously, the PRSM Project Team was going to create Whitepapers and multi-media Trailers to provide additional information to the districts regarding PRSM To Be processes.  Due to the compressed timeframe and resource constraints, the PRSM Project Team has decided to focus their efforts on producing the Trailers, instead of the Whitepapers.  Activities associated to the Trailer development has been added to the PRSM project schedule.  Currently the owner of this activity is identifying resources to assist with this effort.

Risk R-2: Resource Availability

Risk Statement:  Without adequate Caltrans resources working on PRSM, the project implementation schedule could be delayed.  While in the Adaptation Phase, PRSM Project Team members should be allocated full time.  Individual Resources may need to be identified at the task level in the Project Plan in order to estimate resource requirements and availability.

Probability:  Medium	Impact: High 		Time Frame:  Short  	Severity:  High	Assigned to: TBD

IPOC Recommendations:

- R-2a - After the PRSM work plan is complete, determine the resource gaps and reallocate effort as appropriate.

- R-2b - Assign individual resources at the task level in the project schedule to assist in estimating resource requirements.  All PRSM project resources, including vendor resources, should be included.

Status Update:

May 10 Status:	No new status

April 10 Status:	During the September 09 reporting period, a CA Clarity technical resource was unavailable during the business objects migration to virtual environments.  This resulted in a delay of the business object migration task.

Risk R-1:  Business Rules and Business Process Changes

Risk Statement: The impact of business changes resulting from the PRSM implementation needs to be sufficiently understood, planned for, and communicated to Caltrans staff.  If District field staff are not in agreement with the decisions and consequences of changing/standardizing business rules and business processes, it may have an adverse effect on system acceptance and may disrupt work in progress.  This could result in increased resistance to acceptance and usage of the system.

Probability:  High 		Impact:  High 	Time Frame:  Med 	  Severity:  High	Assigned to: David Cordone

IPOC Recommendations:

- R-1a - Implement a formal change management process which will be used for PRSM project related changes.  Change management tasks associated with these changes should be incorporated into the project schedule and budget.  Changes should be communicated to the key stakeholders.

- R-1b - Define the process for gaining field consensus on the new business rules and business processes.

- R-1c - Develop a plan that describes how information on new business rules and business processes will be communicated to the field with sufficient time to get feedback and buy-in.

- R-1d - Expedite the communication of the detailed To-Be Business Process changes to the Districts so that they can gain a better understanding of the impacts and benefits of PRSM.

Status Update:

May 10 Status:	 Per the draft schedule presented during the May 25, 2010 PRSM Project status meeting, the Requirements Baselining effort is scheduled to be completed on June 16, 2010.

April 10 Status:	Per the draft schedule presented during the April 27, 2010 PRSM Project status meeting, the Requirements Baselining effort is scheduled to be completed on May 24, 2010.  There are currently 3 open Project Change Requests (PCR’s) that include changes and/or deletions to existing requirements / functionality (PCR 8, 9, and 12).  The majority of these changes involve interface requirements.  The PRSM Change Management Team has placed these PCR’s on hold until PCR 13 (Developing an Interface to EFIS) has been approved.  An effort is underway to baseline the PRSM requirements.  In addition, the Implementation Vendor is currently in the process of mapping the requirements to the To-Be processes using the requirements tracking application RequisitePro.

General Comments

Deloitte & Touche LLP’s IPOC contract with the Caltrans PRSM project started in December 2008.  This Independent Project Oversight Report (IPOR) provided by Deloitte & Touche LLP has been developed in accordance with the applicable standards of the American Institute of Certified Public Accountants (AICPA) as per Deloitte & Touche LLP policy.  IPOC has attended various PRSM project meetings throughout the month of May, including PRSM Status meetings, PRSM Change Management meetings, PRSM Risk Management meeting, and the PRSM Advisory Committee meeting.

The PRSM project is in the Adaptation Part B Phase of the project.  Five deliverables have been identified to be completed during the Adaptation Phase: Application Installation Report, Data Initialization Plan, Training Role Descriptions and Course List, Training and Documentation Plan and Pilot Plan.  IPOC is planning to review each of these deliverables as they are submitted and will provide comments and feedback.

During the May 2010 reporting period, PRSM project status meetings have begun occurring on a bi-weekly basis versus a weekly basis.  During the status meetings, the Implementation Vendor distributes an updated status report, which includes an updated schedule in Microsoft Project for the current phase.  The schedule provides a detailed view of the status of activities, deliverables, and milestones.  The status report also includes a Past Due Task Status Register and an Action Item / Decision Register.  In addition, PRSM Change Management meetings occur on a bi-weekly basis following the PRSM status meeting.  During these meetings new and open project change requests (PCR’s) are discussed by PRSM Project Management and the Implementation Vendor Project Manager.

Project Change Requests (PCR’s) have been created for changes to and/or deletions of PRSM requirements.  There are currently 3 open Project Change Requests (PCR’s) that include changes and/or deletions to existing requirements / functionality (PCR 8, 9, and 12).  The majority of these changes involve interface requirements.  The PRSM Change Management Team has placed these PCR’s on hold until PCR 13 (Developing an Interface to EFIS) has been approved.

Production equipment has been procured and is onsite being configured.  The training and testing environments have been implemented and business objects have been installed in those environments.  The previous issue with the development environment has been resolved.  The PRSM Action Item / Decision Register includes an issue that involves System Architecture / Performance: Network connectivity for PRSM from OTECH through the last mile connectivity to end user locations.  With new connectivity between the OTECH data center and Caltrans, some level of network bandwidth analysis should be performed to determine potential network issues prior to Go-Live.  This issue is currently being reviewed by the PRSM IT Project Manager.

A new baseline schedule was set with the approved Special Project Report (SPR) dated December 8, 2009.  The SPR states the end date of the Adaptation Phase as February 2010 and the end date of the entire PRSM project as June 13, 2011.  According to the last approved project schedule (presented during the March 2, 2010 PRSM Project status meeting), the Implementation Vendor identified the Adaptation Phase completion date as June 29, 2010 and the PRSM project completion date as October 10, 2011.  This represents a difference of four (4) months or approximately a 57% delay for the Adaptation Phase and an extension of the project by four (4) months or approximately a 15% delay.  In the April 2010 reporting period, the Implementation Vendor re-evaluated the PRSM project schedule and submitted a revised draft schedule.  Since April, the proposed schedule has gone through additional revisions, which resulted in additional delays.  The most recent draft schedule (presented during the May 25, 2010 PRSM Project status meeting), reflects an approximate five (5) month delay from the last approved project schedule for both the Adaptation Phase and the project completion date.  Given this change, IPOC has reported the project as “Behind Schedule”.  For more information, please refer to the Schedule section of Page 1 of this IPOR.

## Project Oversight Review Checklist for May 2010

Project Oversight Review Checklist: High Criticality Project

This checklist is an assessment for the Adaptation Phase. The end date of this phase is June 2010 (per the last approved project schedule).

| Practices and Products | Adequate | Deficient | Notes: Items Reviewed; Interviews Conducted; Demonstration |
| --- | --- | --- | --- |
| Planning and Tracking |
| Have the business case, project goals, objectives, expected outcomes, key stakeholders, and sponsor(s) identified and documented? | X |  | An updated SPR was approved by the OCIO on December 8, 2009. The appropriate project documents should be updated with the new information from the SPR. |
| Has a detailed project plan with all activities (tasks), milestones, dates, and estimated hours by task loaded into project management (PM) software? Are the lowest level tasks of a short duration with measurable outcomes? |  | X | The Implementation Vendor is using a Rolling Wave scheduling approach. Prior to the end of each phase or PRSM Payment Point, the Implementation Vendor and Caltrans work together to develop the specific activities for the tasks in the next Rolling Wave. The new detailed Rolling Wave Plan for the succeeding Project Phase will be documented in MS Project and will be submitted for State Acceptance as a prerequisite for State Acceptance of the current Payment Point. The Implementation Vendor submitted a PRSM Project Implementation Plan during the Planning Phase of the project. The Implementation Plan provides a schedule in MS Project for project activities, milestones, and deliverables including start and finish dates, duration, and high level resource assignments for each task. Currently there is not an approved project schedule that accurately reflects the remainder of the project. In the April 2010 reporting period, the Implementation Vendor re-evaluated the PRSM project schedule and submitted a revised draft schedule. Since April, the proposed schedule has gone through additional revisions, which resulted in additional delays. The most recent draft schedule (presented during the May 25, 2010 PRSM Project status meeting), reflects an approximate five (5) month delay from the last approved project schedule for both the Adaptation Phase and the project completion date. The PRSM project team is currently in the process of reviewing the revised draft schedule and identifying the root causes of the delay. |
| Is completion of planned tasks recorded within the PM software? | X |  | On a bi-weekly basis, current and upcoming tasks are reviewed by the PRSM Project team and completion of planned tasks are updated as necessary. |
| Are actual hours expended by task recorded at least monthly within PM software? | X |  | Actual hours are charged to a WBS and are recorded and tracked in the Department’s official accounting system. An overall project WBS list of approximately 2,000 items exists in MS Excel. |
| Are estimated hours to complete by task recorded at least monthly within PM software? | X |  | On a bi-weekly basis, current and upcoming tasks are reviewed by the PRSM Project team and the estimated hours to complete the tasks are updated as necessary. |
| Is there a formal staffing plan, including a current organization chart, written roles and responsibilities, plans for staff acquisition, schedule for arrival and departure of specific staff, and staff training plans | X |  | Formal staffing plans, including a current organization chart and written roles and responsibilities exist for the Caltrans PRSM Project Team and the Implementation Vendor. |
| Have project cost estimates, with supporting data for each cost category, been maintained? | X |  | The latest approved SPR dated December 8, 2009 has reset the baseline. |
| Are software size estimates developed and tracked? | N/A | N/A | This item is not applicable. |
| Are two or more estimation approaches used to refine estimates? | N/A | N/A | This item is not applicable. |
| Are independent reviews of estimates conducted? | N/A | N/A | This item is not applicable. |
| Are actual costs recorded and regularly compared to budgeted costs? | X |  | A spreadsheet exists that shows planned and actual costs by month. |
| Is supporting data maintained for actual costs? | X |  | Actual costs are obtained from timesheets that allocate time to WBS numbers/tasks. |
| Is completion status of work plan activities, deliverables, and milestones recorded, compared to schedule and included in a written status reporting process? | X |  | Beginning in the May 2009 reporting period, PRSM project status meetings have been occurring on a weekly basis versus bi-weekly. During the meetings, the Implementation Vendor distributes an updated status report, which includes an updated schedule in MS Project for the current phase. The schedule provides a detailed view of the status of activities, deliverables, and milestones for the current phase. In addition, the status report also includes a Past Due Task Status Register and an Action Item / Decision Register. A high-level status report is posted on the Caltrans Improvement Project web database. Status reports go to the Legislature quarterly. |
| Are key specification documents (e.g. contracts, requirement specifications and/or contract deliverables) and software products under formal configuration control, with items to be controlled and specific staff roles and responsibilities for configuration management identified in a configuration management plan? | X |  | The Configuration Management Plan deliverable was submitted by the Implementation Vendor to Caltrans during the Planning Phase. After Caltrans and IPOC performed an initial review of the Plan, the Implementation Vendor submitted an updated version. The current Configuration Management Plan, dated 7/19/2009, provides details on configuration management of key project documents and software products. Configuration requirements baseline, customizations and deleted requirement agreements were reviewed by Caltrans and feedback was provided to the Implementation Vendor. Finalization of interface and conversion requirements has been delayed until the completion of Project Change Request (PCR) 13, which is the change request for the ERP Financial Infrastructure (EFIS) interface. |
| Are issues/problems and their resolution (including assignment of specific staff responsibility for issue resolution and specific deadlines for completion of resolution activities), formally tracked? | X |  | An Issue Management Plan was approved and open issues are in the project database. The IT project manager is considering the same tool for managing project changes. Additionally, Caltrans has established an Issues Management Meeting that is held on a monthly basis. |
| Is user satisfaction assessed at key project milestones? | X |  | Representatives of the engineering areas and regions participated in the vendor demonstration evaluations. In addition, Caltrans scheduled Implementation Team training sessions that provided the PRSM Implementation Team with an overview of PRSM Methodology and Functionality. Training Session #1 occurred during the week of September 14th. After completion of Session #1 training, the PRSM Project Team gathered feedback on the content and the effectiveness of the training and used the feedback to update and/or improve Training Session #2, which occurred during the week of September 28th. This is adequate for the Adaptation Phase of the project. |
| Is planning in compliance with formal standards or a system development life-cycle (SDLC) methodology? | X |  | Compliance with PMBOK standards is adequate for this phase of the project. Five deliverables have been identified to be completed during the Adaptation Phase: Application Installation Report, Data Initialization Plan, Training Role Descriptions and Course List, Training and Documentation Plan and Pilot Plan. IPOC is planning to review each of these deliverables as they are submitted and will provide comments and feedback. |
| Is there formal enterprise architecture in place? | X |  | The RFQI describes the target Caltrans enterprise environment. |
| Are project closeout activities performed, including a PIER, collection and archiving up-to-date project records and identification of lessons learned? | N/A | N/A | Project is in the Adaptation Phase. |
| Procurement |
| Are appropriate procurement vehicles selected (e.g. CMAS, MSA, “alternative procurement”) and their required processes followed? | X |  | The final contract was signed by the Implementation Vendor on February 26, 2009. Caltrans received, reviewed and signed the contract on February 27, 2009. DGS Legal reviewed and signed the contract on March 5th, 2009. |
| Is a detailed written scope of work for all services included in solicitation documents? | X |  | Detailed written scope of work is contained in the RFP. |
| Are detailed requirement specifications included in solicitation documents? | X |  | Detailed requirement specifications are contained in the RFP. Requirements are described in the RFQI and Value Analysis documents. |
| Is there material participation of outside expertise (e.g. DGS, Departmental specialists, consultants) in procurement planning and execution? | X |  | Outside expertise and counsel has been sought from DOF, DGS, and consultants. |
| For large-scale outsourcing, is qualified legal counsel obtained? | N/A | N/A | The project does not involve outsourcing as currently defined. |
| Risk Management |
| Is formal continuous risk management performed, including development of a written risk management plan, identification, analysis, mitigation and escalation of risks in accordance with DOF/TOSU Guidelines, and regular management team review of risks and mitigation progress performed? | X |  | The latest version of the Risk Management Plan was submitted April 30, 2009. Risk owners have been assigned. A Risk Register was developed and is tracked by the Risk Manager. |
| Does the management team review risks and mitigation progress at least monthly? | X |  | Risk Management meetings are being held monthly with the PRSM Project Team where risks and their associated mitigation progress are reviewed. |
| Are externally developed risk identification aids used, such as the SEI Taxonomy Based Questionnaire? | X |  | A risk list was initially populated using the SEI Risk Taxonomy. Additional risks are added to the list migration from the issue list. |
| Communication |
| Is there a written project communications plan? | X |  | The latest version of the finalized and approved Communications Plan is dated 6/22/2009. |
| Are regular written status reports prepared and provided to the project manager, department CIO (if applicable) and other key stakeholders? | X |  | The Advisory Committee receives a written status report during the monthly Advisory Committee meetings. These reports include issues identified, changes to scope, schedule, cost, problems encountered, and items accomplished. |
| Are there written escalation policies for issues and risks? | X |  | Both the Risk Management Plan and the Issue Management Plan contain a risk escalation process. |
| Is there regular stakeholder involvement in major project decisions, issue resolution and risk mitigation? | X |  | Implementation Manager meetings occur on a monthly basis. The purpose of this meeting is to keep the District project managers regularly updated on the status of the project and to receive their input. |
| System Engineering |
| Are users involved throughout the project, especially in requirements specification and testing? | X |  | Representatives of key stakeholder groups participated in and reviewed the Value Analysis Report that describes the PRSM requirements. The PRSM Project Team is being run by Caltrans Division of Project management which is the primary constituency for the system. |
| Do users formally approve/sign-off on written specifications? | X |  | Representatives of key stakeholder groups participated in and reviewed the Value Analysis Report that describes the PRSM requirements. In addition, the Implementation Vendor has been delivering a series of Checkpoints, which include a review of the PRSM configurations and design documentation. After each checkpoint, the PRSM Project Team gathers and consolidates their feedback on what was presented and provides it to the Implementation Vendor. The Implementation Vendor originally stated that there would be four (4) checkpoints over the course of the Adaptation Phase. In the March 2010 reporting period, the implementation Vendor stated that the remainder of the configurations would be presented in Checkpoint 4 or any of number of checkpoints needed. Checkpoint 4 was performed in April 2010. The walkthrough included the review of the revised design documentation for configurations presented in previous checkpoints. Configuration requirements baseline, customizations and deleted requirement agreements were reviewed by Caltrans and feedback was provided to the Implementation Vendor. |
| Is a formal SDLC methodology followed? | X |  | The Implementation Vendor is using the SDLC Stage Gate Model to manage the configuration and customization of PRSM throughout the Adaptation Phase. In this model, work packages divide the total effort into a series of stages, where gating criteria must be met prior to moving from one stage to the next. For the PRSM Project, each work package is designed, developed, tested, and accepted prior to completion of the package. This model may have an impact on the schedule, due to the amount of review time for each work package. In order to offset this, Caltrans is incorporating review cycles through the new checkpoint implementation approach. |
| Is a software product used to assist in managing requirements? Is there tracking of requirements traceability through all life-cycle phases? | X |  | An Implementation and System Acceptance Test consultant has been added to the team. The level of requirements management presently in place appears to be appropriate for the current phase of the project. |
| Do software engineering standards exist and are they followed? | X |  | Engineering standards exist and are documented in the PRSM Configuration Management Plan. IPOC will monitor the project during the Adaptation Phase and subsequent phases to determine how effectively the PRSM Project is adhering to the engineering standards. |
| Does product defect tracking begin no later than requirements specifications? | X |  | The PRSM issue management system currently is designed to serve as a defect tracking mechanism. Several of the issues already raised represent clarification to requirements. |
| Are formal code reviews conducted? | N/A | N/A | This is not applicable for this project. However, the PRSM Project Team has planned for formal configuration reviews to occur during checkpoints throughout the Adaptation Phase. In the March 2010 reporting period, the implementation Vendor stated that the remainder of the configurations would be presented in Checkpoint 4 or any of number of checkpoints needed. Checkpoint 4 was performed in April 2010. The walkthrough included the review of the revised design documentation for configurations presented in previous checkpoints. Configuration requirements baseline, customizations and deleted requirement agreements were reviewed by Caltrans and feedback was provided to the Implementation Vendor. |
| Are formal quality assurance procedures followed consistently? | X |  | The PRSM Project follows the State Acceptance process for deliverables. There are three types of Acceptance: Acceptance Type 1 – Objective on Receipt; Acceptance Type 2 – Non-Software Acceptance; and Acceptance Type 3 – Software Acceptance Testing by the State. |
| Do users sign-off on acceptance test results before a new system or changes are put into production? | N/A | N/A | Project is in the Adaptation Phase |
| Is the enterprise architecture plan adhered to? | X |  | Caltrans is in the process of creating a formal enterprise architecture plan. The PRSM technology solution was requested to be submitted as part of the study. |
| Are formal deliverable inspections performed, beginning with requirements specifications? | X |  | An effort is underway to baseline the requirements. Although the majority of requirements are baselined, there are 3 open Project Change Requests (PCR’s) that will need to be approved before the requirements baseline effort can be completed (PCR 8, 9, and 12). In addition, the Implementation Vendor is currently in the process of mapping the requirements to the To-Be processes using the requirements tracking application RequisitePro. This traceability activity is also dependent on the approval of the 3 open PCR’s. Previously, the requirements have been through two separate review activities: user group review and IV&V review. There is a third review underway by the Project Management team in order to document the As-Is and To-Be business processes. IPOC will continue to monitor this area as the project progresses. |
| Are IV&V services obtained and used? | X |  | The IV&V Contract was approved and the IV&V Vendor began work in April 2008. |

## IPO Report for April 2010

# Independent Project Oversight Report

| Project Name: | Caltrans PRSM | Assessment Date: | April 30, 2010 |
| --- | --- | --- | --- |
|  | Frequency: |  |

Oversight Provider Information

| Oversight Leader: | Greg Thomas | Organization: | Deloitte & Touche LLP |
| --- | --- | --- | --- |
| Phone Number: | 415 783 5211 | Email: | grethomas@deloitte.com |

Project Information

| Project Number: | 2660-160 | Department: | Transportation (Caltrans) |
| --- | --- | --- | --- |
| Criticality: | High | Agency: | Business, Transportation & Housing |
| Last Approved Document/Date: | SPR (12/08/09) | Total One-time Cost: | $26,078,375 |
| Start Date: | June 7, 2000 | End Date: | June 13, 2011 |
| Project Manager: | David Youmans | Organization: | Caltrans |
| Phone Number: | 916.826.4425 | Email: | david_youmans@dot.ca.gov |

Summary: Current Status

| Project Phase: | Adaptation |
| --- | --- |
| Planned Start Date: | May 20, 2009 | Planned End Date: | February 2, 2010 |
| Actual Start Date: | July 1, 2009 | Forecasted End Date: June 29, 2010 |

Schedule

Select the statement that most closely applies, measured against the last Finance approved document.

| Behind Schedule | Ahead-of-schedule: One or more major tasks or milestones have been completed and approved early (> 5%). All other major tasks and milestones completed and approved according to plan. On-schedule: All major tasks and milestones have been completed and approved according to plan. (Within 5%) Behind Schedule: One or more major tasks or milestones are expected to be delayed. (> 5%) |
| --- | --- |
| Comments: | A new baseline schedule was set with the approved SPR dated December 8, 2009. The SPR states the end date of the Adaptation Phase as February 2010. In the March 2, 2010 PRSM Project status meeting, the Implementation Vendor identified the Adaptation Phase completion date as June 29, 2010. For the Adaptation Phase, this represents a difference of four (4) months or approximately a 57% delay. Additionally, the SPR states the end date of the entire PRSM project as June 13, 2011. In the March 2, 2010 PRSM Project Status meeting, the Implementation Vendor identified the PRSM Project completion date as October 10, 2011. This represents an extension of the project by four (4) months or approximately a 15% delay. Given this change, IPOC has reported the project as “Behind Schedule”. In the April 2010 reporting period, the Implementation Vendor re-evaluated the PRSM project schedule and submitted a revised draft schedule, which reflects an additional four (4) month delay in the Adaptation Phase. The PRSM project team is currently in the process of reviewing the revised draft schedule and identifying the root causes of the delay. Please note that while the Draft schedule is showing additional delays, efforts by the PRSM Project Team (such as concurrent configuration of agreed upon requirements) are currently underway to offset some of the delay in Adaptation. We will continue to closely monitor the schedule status during the Adaptation Phase and report any updates as they occur. Please refer to the PRSM Project Schedule issue in the Issue section below for information regarding further potential impacts to the schedule. |

Resources (Level of Effort) Choose the statement that most closely applies.

| Within Resources | Fewer Resources Completion of one or more major tasks and/or acceptable products has required or is expected to require materially (>5%) fewer hours/staff than planned. Within Resources All major tasks have been completed and acceptable products created using the planned number of hours/staff (within 5%). More Resources Completion of major tasks and/or acceptable products has required or is expected to require materially (>5%) more hours/staff than planned. |
| --- | --- |
| Comments: | A new baseline was set with the approved SPR dated 12/08/2009. |

Resources (Budget/Cost) Choose the statement that most closely applies.

| Within Cost | Less cost The project is (>5%) under budget. Within cost The project is operating within budget. Higher cost Material budget increases (>5%) are likely. |
| --- | --- |
| Comments: | A new baseline was set with the approved SPR dated 12/08/2009. |

Quality (Client Functionality) Choose the statement that most closely applies.

| Inadequately Defined | Adequately Defined Required client functionality is adequately defined, and is being successfully built into the system, given the current project phase. Inadequately Defined One or more significant components of required client functionality are inadequately defined, or are not being successfully built into the system, given the current project phase. |
| --- | --- |
| Comments: | Client functionality (scope) is not adequately defined for the Adaptation Phase which began on July 1, 2009. The revised draft PRSM Project Schedule, which was submitted by the Implementation Vendor during the April 2010 reporting period showed an additional delay in the Adaptation Phase of approximately four (4) months. Please refer to the Schedule section above for additional information. Through inspection of the revised draft schedule, it was noted that one of the items which may have impacted the delay in Adaptation is the Requirements Baselining effort, which includes the analysis and approval of Project Change Request’s (PCR’s) 8, 9, and 12. Please note that PCR’s 8, 9, and 12 are currently open and represent changes and/or deletions to existing requirements / functionality. The majority of these changes involve interface requirements. In addition, another area which may have impacted the delay in Adaptation is the ERP Financial Infrastructure (EFIS) Interface development effort. The PRSM Project Team has been made aware that Caltrans Financial Data to Oracle (FIDO) system and Earned Value Reporting System (EVRS) are going to be phased out once the EFIS has been implemented. Based on this information, the PRSM Project Team has created PCR 13, which involves building an interface to EFIS. Per the revised draft schedule presented during the April 27, 2010 PRSM Project status meeting, the Requirements Baselining effort is scheduled to be completed on May 24, 2010. The PRSM Project Team is working closely with the Implementation Vendor to close out PCR’s 8, 9, 12, and 13. Once this effort has been completed and PCR’s 8, 9, 12, and 13 are closed, functionality should be adequately defined for the Adaptation Phase. Please refer to the Project Change Requests Finalization and Approval risk in the New Risks section below for information regarding further potential impacts to the schedule. In addition to the open PCR’s, another area which may have had an impact on the potential delay in Adaptation is the uncertainty around the percent complete for configuration. The PRSM Project Team has been monitoring the following risk (Risk #80 on the PRSM Risk Log) identified by the IV&V Vendor: Clarity configuration checkpoints have not been effective at measuring project progress. A requirements traceability matrix showing the configuration status of each requirement has not been produced. It is unclear how many of the configurations have been completed and if the configurations are on schedule. The PRSM Project Team is currently having discussions with the Implementation Vendor to determine the percentage of configuration that has been completed at this stage. We will continue to closely monitor the functionality status during the Adaptation Phase and report any updates as they occur. |

Quality (Architecture/System Performance) Choose the statement that most closely applies.

|  | Adequately Defined The system technical architecture is adequately defined, and modeling, benchmarking and testing are being conducted (or are planned) appropriate to the current project phase. Inadequately Defined The system technical architecture is not adequately defined, or modeling, benchmarking and testing are not being conducted (or are planned) appropriate to the current project phase. |
| --- | --- |
| Comments: | System technical architecture and performance are adequately defined for the Adaptation Phase. The Implementation Vendor has submitted a Configuration Management Plan, High Level Design, and updated Architecture Diagram. The Production environment hardware has been configured and turned over to Caltrans. The software applications are currently being installed and tested. The previous issue with the development environment has been resolved. |

Issues

*New Issue: PRSM Project Schedule

Issue Statement: In the April 2010 reporting period, the Implementation Vendor submitted a revised draft PRSM Project Schedule.  This draft schedule reflected an additional 4 month delay to the Adaptation Phase.  At this point in time, the Caltrans PRSM Project team and the Implementation Vendor are not in agreement with the dates in the revised draft schedule.

Impact: High	Time Frame:  Short Term	Severity:  High	Assigned to: David Youmans

IPOC Recommendations:

- IPOC recommends that the revised draft schedule is vetted with the PRSM Project Team, the Implementation Vendor, and Project Stakeholders and a consensus/agreement on the finalized schedule is completed by the end of the next reporting period (May 2010).

- In addition to the resolution of the PRSM Project Schedule, any cost impact associated with the additional delays in the schedule should be determined by the end of the next reporting period (May 2010).

Issue Title: EFIS Interface

Issue Statement: The PRSM Project Team has been made aware that Caltrans Financial Data to Oracle (FIDO) system and Earned Value Reporting System (EVRS) are going to be phased out once the ERP Financial Infrastructure (EFIS) has been implemented.  While developing to one standard interface presents a business opportunity, specifications and data requirements will need to be analyzed and documented.  The development of the EFIS interface is a critical step for the PRSM project to proceed to the Pilot phase.  Currently EFIS is scheduled to go-live in July 2010 and PRSM is scheduled to begin Pilot on 6/28/2010.  A delay in the EFIS schedule could significantly delay the PRSM pilot and roll out to the Districts.   In addition, the development of the EFIS interface could impact the cost of PRSM.  There are three (3) potential scenarios related to this issue that could impact the schedule and/or cost: 1) a delay in the EFIS project could result in a delay to PRSM; 2) the complexity of the interface to EFIS and the activities/tasks involved could result in a delay to PRSM and/or impact cost; and 3) a delay in the EFIS training schedule could conflict with the PRSM training schedule, which could result in a delay to PRSM.

Impact: High	Time Frame:  Short Term	Severity:  High	Assigned to: Jacqueline Moore

IPOC Recommendations:

- Develop a detailed action plan for the EFIS interface that addresses the following: impact to the data conversion effort, impact to districts and end users, impact to project resources, impact to schedule, and impact to costs.

- Update the PRSM project schedule with the activities associated with the EFIS interface, including analysis activities.

- Continue to work closely with the EFIS project by attending the bi-weekly interface planning meetings.  Escalate issues related to EFIS timing and resource needs to the PRSM Steering Committee for resolution as soon as the interface requirements are finalized.

Status Update:

April 10 Status:	Per the draft schedule presented during the April 27, 2010 PRSM Project status meeting, EFIS data conversion activities are scheduled to be completed in June 2010.  In addition, the EFIS Development effort (including Integration Testing) is scheduled to be completed in September 2010.

Mar 10 Status:	An impact analysis is currently being performed for the EFIS interface change request (PCR 13).  The PRSM Project Team continues to meet with the EFIS Project Team on a weekly basis.  According to the PRSM Project Schedule dated March 23, 2010, EFIS data conversion activities are scheduled to be completed in May 2010.  In addition three (3) EFIS risks have been added to the PRSM Risk Log, risks 76A, 76B, and 77.  These risks are discussed during the monthly PRSM Risk Management meeting.  The next PRSM Risk Management meeting is scheduled for May 5th.

New Risks

*New Risk: Project Change Requests Finalization and Approval

Risk Statement: The delay and uncertainty in approving Project Change Request’s 8,9,12, and 13 could have further impact on the schedule and cost of the project.

Probability:  High        Impact: High     Time Frame:  Short Term	   Severity:  High	       Assigned to: David Youmans

Recommendation:

- IPOC recommends that PCR 8, 9, 12, and 13 are clarified and approved by the end of the next reporting period (May 2010).

Progress Toward Addressing Prior Risks

Risk Title: PRSM Task Dependency Identification

Risk Statement: Recent activities to refresh/reevaluate the schedule have resulted in a significant number of previous unknown dependencies between interface development activities, configuration activities, and data conversion activities.  The identification of these could result in further delay to the overall project schedule.

Probability:  High        Impact: High     Time Frame:  Long Term	   Severity:  High	       Assigned to: David Youmans

Recommendation:

- During the weekly PRSM Project Status meetings, IPOC recommends that each of the Caltrans PRSM Project Team Workgroups conduct brief and more frequent status meetings regarding status of tasks, dependencies, risks and issues associated with those tasks.  In addition, IPOC recommends that the PRSM Project Team continues to refine the schedule for project phases after Adaptation to ensure that any risk of further schedule slippage is mitigated and so that the total impact of known dependencies on the schedule can be understood and communicated to stakeholders.

Status Update:

April 10 Status:	No new status

Mar 10 Status:	The PRSM Project Team has continued to reevaluate the PRSM Project Schedule during the month of December.  During the weekly PRSM Project Status meetings, current and up-coming tasks are discussed and risks and dependencies associated with those tasks are identified.  For a status update on the requirements baselining process, please refer to Risk: Business Rules and Business Process Changes below.

Risk Title: PRSM Project Team Communications

Risk Statement: Effective, clear and frequent communications between the Caltrans PRSM team, the Implementation Vendor, other vendors (e.g., testing and data conversion), and District stakeholder is critical given the size and complexity of PRSM during the Adaptation Phase.  The new Communications Plan, while documented, needs to be fully implemented early in the Adaptation Phase.  Without effective communications, the PRSM project schedule, scope and quality could be difficult to manage and control.

Probability:  Medium        Impact: High     Time Frame:  Long Term	   Severity:  High	       Assigned to: David Youmans

IPOC Recommendations:

- In addition to the weekly PRSM Project Status meetings, IPOC recommends that Caltrans PRSM Project Management and Implementation Vendor Project Management conduct frequent status meetings in order to discuss the status of high priority issues and action items.  These checkpoint meetings should be no longer than ½ hour in duration and conducted twice per week (i.e., Monday AM and Thursday PM).

- Expedite the communication of the detailed To-Be Business Process changes to the Districts so that they can gain a better understanding of the impacts and benefits of PRSM.

Status Update:

April 10 Status:	No new status

Mar 10 Status:	Beginning in January 2010, project risks have been added as a discussion point during the weekly PRSM project status meetings.  During this discussion, a select number of risks are discussed, including their current status, impact, and remediation steps.  The Communications Plan was formally approved in the month of August and provides details surrounding the methods of communication for the PRSM project.  PRSM Project Status meetings continue to occur on a weekly basis.  PRSM sub-teams meet at a minimum of once a week to discuss current and upcoming tasks.  In addition to the PRSM Project Team meetings, Caltrans prepares and distributes a monthly newsletter and “Nuggets of Knowledge” memo to the districts.  Implementation Team training sessions have been scheduled during the month of September that will provide the PRSM Implementation Team with an overview of PRSM Methodology and Functionality.  Previously, the PRSM Project Team was going to create Whitepapers and multi-media Trailers to provide additional information to the districts regarding PRSM To Be processes.  Due to the compressed timeframe and resource constraints, the PRSM Project Team has decided to focus their efforts on producing the Trailers, instead of the Whitepapers.  Activities associated to the Trailer development has been added to the PRSM project schedule.  Currently the owner of this activity is identifying resources to assist with this effort.

Risk Title: Resource Availability

Risk Statement:  Without adequate Caltrans resources working on PRSM, the project implementation schedule could be delayed.  While in the Adaptation Phase, PRSM Project Team members should be allocated full time.  Individual Resources may need to be identified at the task level in the Project Plan in order to estimate resource requirements and availability.

Probability:  Medium	Impact: High 		Time Frame:  Short  	Severity:  High	Assigned to: TBD

IPOC Recommendations:

- After the PRSM work plan is complete, determine the resource gaps and reallocate effort as appropriate.

- Assign individual resources at the task level in the project schedule to assist in estimating resource requirements.  All PRSM project resources, including vendor resources, should be included.

Status Update:

April 10 Status:	No new status

Mar 10 Status:	During the September 09 reporting period, a CA Clarity technical resource was unavailable during the business objects migration to virtual environments.  This resulted in a delay of the business object migration task.

Risk Title:  Business Rules and Business Process Changes

Risk Statement: The impact of business changes resulting from the PRSM implementation needs to be sufficiently understood, planned for, and communicated to Caltrans staff.  If District field staff are not in agreement with the decisions and consequences of changing/standardizing business rules and business processes, it may have an adverse effect on system acceptance and may disrupt work in progress.  This could result in increased resistance to acceptance and usage of the system.

Probability:  High 	Impact:  High 	Time Frame:  Med 	  Severity:  High	Assigned to: David Cordone

IPOC Recommendations:

- Implement a formal change management process which will be used for PRSM project related changes.  Change management tasks associated with these changes should be incorporated into the project schedule and budget.  Changes should be communicated to the key stakeholders.

- Define the process for gaining field consensus on the new business rules and business processes.

- Develop a plan that describes how information on new business rules and business processes will be communicated to the field with sufficient time to get feedback and buy-in.

- Expedite the communication of the detailed To-Be Business Process changes to the Districts so that they can gain a better understanding of the impacts and benefits of PRSM.

Status Update:

April 10 Status:	Per the revised draft schedule presented during the April 27, 2010 PRSM Project status meeting, the Requirements Baselining effort is scheduled to be completed on May 24, 2010.

Mar 10 Status:	There are currently 3 open Project Change Requests (PCR’s) that include changes and/or deletions to existing requirements / functionality (PCR 8, 9, and 12).  The majority of these changes involve interface requirements.  The PRSM Change Management Team has placed these PCR’s on hold until PCR 13 (Developing an Interface to EFIS) has been approved.  An effort is underway to baseline the PRSM requirements.  In addition, the Implementation Vendor is currently in the process of mapping the requirements to the To-Be processes using the requirements tracking application RequisitePro.

General Comments

Deloitte & Touche LLP’s IPOC contract with the Caltrans PRSM project started in December 2008.  This Independent Project Oversight Report (IPOR) provided by Deloitte & Touche LLP has been developed in accordance with the applicable standards of the American Institute of Certified Public Accountants (AICPA) as per Deloitte & Touche LLP policy.  IPOC has attended various PRSM project meetings throughout the month of April, including PRSM Status meetings, PRSM Change Management meetings, the PRSM Implementation Managers meeting, PRSM Risk Management meeting, and the PRSM Advisory Committee meeting.

The PRSM project is in the Adaptation Part B Phase of the project.  Five deliverables have been identified to be completed during the Adaptation Phase: Application Installation Report, Data Initialization Plan, Training Role Descriptions and Course List, Training and Documentation Plan and Pilot Plan.  IPOC is planning to review each of these deliverables as they are submitted and will provide comments and feedback.

PRSM project status meetings occur on a weekly basis.  During the status meetings, the Implementation Vendor distributes an updated status report, which includes an updated schedule in Microsoft Project for the current phase.  The schedule provides a detailed view of the status of activities, deliverables, and milestones.  The status report also includes a Past Due Task Status Register and an Action Item / Decision Register.  In addition, PRSM Change Management meetings occur on a weekly basis following the PRSM status meeting.  During these meetings new and open project change requests (PCR’s) are discussed by PRSM Project Management and the Implementation Vendor Project Manager.

The Implementation Vendor has submitted an Adaptation Phase schedule to Caltrans, which separates the Adaptation Phase into two parts (A and B).  In addition, the Implementation Plan was submitted, which was reviewed by Caltrans, and includes a schedule for the entire project.  The Implementation Vendor is using a Rolling Wave scheduling process for the PRSM project where a more detailed schedule is prepared before the start of each project phase.  Prior to the end of each phase or PRSM Payment Point, the Implementation Vendor and Caltrans will work together to develop the specific activities for the tasks in the next Rolling Wave.  In October 2009, the Implementation Vendor proposed a new implementation approach to replace the iterative work package approach.   This new approach involves establishing a series of checkpoints throughout the remainder of the Adaptation Phase.  During each checkpoint, configured or customized functionality is reviewed by the PRSM Project Team through meetings facilitated by the Implementation Vendor.

Project Change Requests (PCR’s) have been created for changes to and/or deletions of PRSM requirements.  There are currently 3 open Project Change Requests (PCR’s) that include changes and/or deletions to existing requirements / functionality (PCR 8, 9, and 12).  The majority of these changes involve interface requirements.  The PRSM Change Management Team has placed these PCR’s on hold until PCR 13 (Developing an Interface to EFIS) has been approved.

Production equipment has been procured and is onsite being configured.  The training and testing environments have been implemented and business objects have been installed in those environments.  The previous issue with the development environment has been resolved.  The PRSM Action Item / Decision Register includes an issue that involves System Architecture / Performance: Network connectivity for PRSM from OTECH through the last mile connectivity to end user locations.  With new connectivity between the OTECH data center and Caltrans, some level of network bandwidth analysis should be performed to determine potential network issues prior to Go-Live.  This issue is currently being reviewed by the PRSM IT Project Manager.

A new baseline schedule was set with the approved SPR dated December 8, 2009.  The SPR states the end date of the Adaptation Phase as February 2010.  In the March 2, 2010 PRSM Project status meeting, the Implementation Vendor identified the Adaptation Phase completion date as June 29, 2010.  For the Adaptation Phase, this represents a difference of four (4) months.  Additionally, the SPR states the end date of the entire PRSM project as June 13, 2011.  In the March 2, 2010 PRSM Project Status meeting, the Implementation Vendor identified the PRSM Project completion date as October 10, 2011.  This represents an extension of the project by four (4) months.  Given this change, IPOC has reported the project as “Behind Schedule”.  For more information, please refer to the Schedule section of Page 1 of this IPOR.

In the April 2010 reporting period, the Implementation Vendor re-evaluated the PRSM project schedule and submitted a revised draft schedule, which reflects an additional four (4) month delay in the Adaptation Phase.   The PRSM project team is currently in the process of reviewing the revised draft schedule and identifying the root causes of the delay.  Please note that while the Draft schedule is showing additional delays, efforts by the PRSM Project Team (such as concurrent configuration of agreed upon requirements) are currently underway to offset some of the delay in Adaptation.  We will continue to closely monitor the schedule status during the Adaptation Phase and report any updates as they occur.

## Project Oversight Review Checklist for April 2010

Project Oversight Review Checklist: High Criticality Project

This checklist is an assessment for the Adaptation Phase. The end date of this phase is June 2010.

| Practices and Products | Adequate | Deficient | Notes: Items Reviewed; Interviews Conducted; Demonstration |
| --- | --- | --- | --- |
| Planning and Tracking |
| Have the business case, project goals, objectives, expected outcomes, key stakeholders, and sponsor(s) identified and documented? | X |  | An updated SPR was approved by the OCIO on December 8, 2009. The appropriate project documents should be updated with the new information from the SPR. |
| Has a detailed project plan with all activities (tasks), milestones, dates, and estimated hours by task loaded into project management (PM) software? Are the lowest level tasks of a short duration with measurable outcomes? | X |  | The Implementation Vendor submitted a PRSM Project Implementation Plan during the Planning Phase of the project. The Implementation Plan provides a schedule in MS Project for project activities, milestones, and deliverables including start and finish dates, duration, and high level resource assignments for each task. The Implementation Vendor is using a Rolling Wave scheduling approach. Prior to the end of each phase or PRSM Payment Point, the Implementation Vendor and Caltrans work together to develop the specific activities for the tasks in the next Rolling Wave. The new detailed Rolling Wave Plan for the succeeding Project Phase will be documented in MS Project and will be submitted for State Acceptance as a prerequisite for State Acceptance of the current Payment Point. In addition, the Implementation Vendor has been delivering a series of Checkpoints, which include a review of the PRSM configurations and design documentation. After each checkpoint, the PRSM Project Team gathers and consolidates their feedback on what was presented and provides it to the Implementation Vendor. The Implementation Vendor originally stated that there would be four (4) checkpoints over the course of the Adaptation Phase. In the March 2010 reporting period, the implementation Vendor stated that the remainder of the configurations would be presented in Checkpoint 4 or any of number of checkpoints needed. Checkpoint 4 was performed in April 2010. The walkthrough included the review of the revised design documentation for configurations presented in previous checkpoints. Configuration requirements baseline, customizations and deleted requirement agreements were reviewed by Caltrans and feedback was provided to the Implementation Vendor. Configuration requirements baseline, customizations and deleted requirement agreements were reviewed by Caltrans and feedback was provided to the Implementation Vendor. Finalization of interface and conversion requirements has been delayed until the completion of Project Change Request (PCR) 13, which is the change request for the ERP Financial Infrastructure (EFIS) interface. Rolling Wave Two was closed out and RW 2 activities not completed were moved to Rolling Wave 3. Rolling Wave 3 activities include completing configurations, developing interfaces and conversion processes, testing configurations and interfaces, and developing the training materials. In the April 2010 reporting period, the Implementation Vendor re-evaluated the PRSM project schedule and submitted a revised draft schedule, which reflects an additional four (4) month delay in the Adaptation Phase. The PRSM project team is currently in the process of reviewing the revised schedule and identifying the root causes of the delay. |
| Is completion of planned tasks recorded within the PM software? | X |  | In October 2009, the Implementation Vendor proposed a new implementation approach to replace the iterative work packages. This new approach involves establishing a series of checkpoints throughout the remainder of the Adaptation Phase. During each checkpoint, configured or customized functionality is reviewed by the PRSM Project Team through meetings facilitated by the Implementation Vendor. On a weekly basis, current and upcoming tasks are reviewed by the PRSM Project team and completion of planned tasks are updated as necessary. |
| Are actual hours expended by task recorded at least monthly within PM software? | X |  | Actual hours are charged to a WBS and are recorded and tracked in the Department’s official accounting system. An overall project WBS list of approximately 2,000 items exists in MS Excel. |
| Are estimated hours to complete by task recorded at least monthly within PM software? | X |  | On a weekly basis, current and upcoming tasks are reviewed by the PRSM Project team and the estimated hours to complete the tasks are updated as necessary. |
| Is there a formal staffing plan, including a current organization chart, written roles and responsibilities, plans for staff acquisition, schedule for arrival and departure of specific staff, and staff training plans | X |  | Formal staffing plans, including a current organization chart and written roles and responsibilities exist for the Caltrans PRSM Project Team and the Implementation Vendor. |
| Have project cost estimates, with supporting data for each cost category, been maintained? | X |  | The latest approved SPR dated December 8, 2009 has reset the baseline. |
| Are software size estimates developed and tracked? | N/A | N/A | This item is not applicable. |
| Are two or more estimation approaches used to refine estimates? | N/A | N/A | This item is not applicable. |
| Are independent reviews of estimates conducted? | N/A | N/A | This item is not applicable. |
| Are actual costs recorded and regularly compared to budgeted costs? | X |  | A spreadsheet exists that shows planned and actual costs by month. |
| Is supporting data maintained for actual costs? | X |  | Actual costs are obtained from timesheets that allocate time to WBS numbers/tasks. |
| Is completion status of work plan activities, deliverables, and milestones recorded, compared to schedule and included in a written status reporting process? | X |  | Beginning in the May 2009 reporting period, PRSM project status meetings have been occurring on a weekly basis versus bi-weekly. During the meetings, the Implementation Vendor distributes an updated status report, which includes an updated schedule in MS Project for the current phase. The schedule provides a detailed view of the status of activities, deliverables, and milestones for the current phase. In addition, the status report also includes a Past Due Task Status Register and an Action Item / Decision Register. A high-level status report is posted on the Caltrans Improvement Project web database. Status reports go to the Legislature quarterly. |
| Are key specification documents (e.g. contracts, requirement specifications and/or contract deliverables) and software products under formal configuration control, with items to be controlled and specific staff roles and responsibilities for configuration management identified in a configuration management plan? | X |  | The Configuration Management Plan deliverable was submitted by the Implementation Vendor to Caltrans during the Planning Phase. After Caltrans and IPOC performed an initial review of the Plan, the Implementation Vendor submitted an updated version. The current Configuration Management Plan, dated 7/19/2009, provides details on configuration management of key project documents and software products. |
| Are issues/problems and their resolution (including assignment of specific staff responsibility for issue resolution and specific deadlines for completion of resolution activities), formally tracked? | X |  | An Issue Management Plan was approved and open issues are in the project database. The IT project manager is considering the same tool for managing project changes. Additionally, Caltrans has established an Issues Management Meeting that is held on a monthly basis. |
| Is user satisfaction assessed at key project milestones? | X |  | Representatives of the engineering areas and regions participated in the vendor demonstration evaluations. In addition, Caltrans scheduled Implementation Team training sessions that provided the PRSM Implementation Team with an overview of PRSM Methodology and Functionality. Training Session #1 occurred during the week of September 14th. After completion of Session #1 training, the PRSM Project Team gathered feedback on the content and the effectiveness of the training and used the feedback to update and/or improve Training Session #2, which occurred during the week of September 28th. This is adequate for the Adaptation Phase of the project. |
| Is planning in compliance with formal standards or a system development life-cycle (SDLC) methodology? | X |  | Compliance with PMBOK standards is adequate for this phase of the project. Five deliverables have been identified to be completed during the Adaptation Phase: Application Installation Report, Data Initialization Plan, Training Role Descriptions and Course List, Training and Documentation Plan and Pilot Plan. IPOC is planning to review each of these deliverables as they are submitted and will provide comments and feedback. |
| Is there formal enterprise architecture in place? | X |  | The RFQI describes the target Caltrans enterprise environment. |
| Are project closeout activities performed, including a PIER, collection and archiving up-to-date project records and identification of lessons learned? | N/A | N/A | Project is in the Adaptation Phase. |
| Procurement |
| Are appropriate procurement vehicles selected (e.g. CMAS, MSA, “alternative procurement”) and their required processes followed? | X |  | The final contract was signed by the Implementation Vendor on February 26, 2009. Caltrans received, reviewed and signed the contract on February 27, 2009. DGS Legal reviewed and signed the contract on March 5th, 2009. |
| Is a detailed written scope of work for all services included in solicitation documents? | X |  | Detailed written scope of work is contained in the RFP. |
| Are detailed requirement specifications included in solicitation documents? | X |  | Detailed requirement specifications are contained in the RFP. Requirements are described in the RFQI and Value Analysis documents. |
| Is there material participation of outside expertise (e.g. DGS, Departmental specialists, consultants) in procurement planning and execution? | X |  | Outside expertise and counsel has been sought from DOF, DGS, and consultants. |
| For large-scale outsourcing, is qualified legal counsel obtained? | N/A | N/A | The project does not involve outsourcing as currently defined. |
| Risk Management |
| Is formal continuous risk management performed, including development of a written risk management plan, identification, analysis, mitigation and escalation of risks in accordance with DOF/TOSU Guidelines, and regular management team review of risks and mitigation progress performed? | X |  | The latest version of the Risk Management Plan was submitted April 30, 2009. Risk owners have been assigned. A Risk Register was developed and is tracked by the Risk Manager. |
| Does the management team review risks and mitigation progress at least monthly? | X |  | Risk Management meetings are being held monthly with the PRSM Project Team where risks and their associated mitigation progress are reviewed. |
| Are externally developed risk identification aids used, such as the SEI Taxonomy Based Questionnaire? | X |  | A risk list was initially populated using the SEI Risk Taxonomy. Additional risks are added to the list migration from the issue list. |
| Communication |
| Is there a written project communications plan? | X |  | The latest version of the finalized and approved Communications Plan is dated 6/22/2009. |
| Are regular written status reports prepared and provided to the project manager, department CIO (if applicable) and other key stakeholders? | X |  | The Advisory Committee receives a written status report during the monthly Advisory Committee meetings. These reports include issues identified, changes to scope, schedule, cost, problems encountered, and items accomplished. |
| Are there written escalation policies for issues and risks? | X |  | Both the Risk Management Plan and the Issue Management Plan contain a risk escalation process. |
| Is there regular stakeholder involvement in major project decisions, issue resolution and risk mitigation? | X |  | Implementation Manager meetings occur on a monthly basis. The purpose of this meeting is to keep the District project managers regularly updated on the status of the project and to receive their input. |
| System Engineering |
| Are users involved throughout the project, especially in requirements specification and testing? | X |  | Representatives of key stakeholder groups participated in and reviewed the Value Analysis Report that describes the PRSM requirements. The PRSM Project Team is being run by Caltrans Division of Project management which is the primary constituency for the system. |
| Do users formally approve/sign-off on written specifications? | X |  | Representatives of key stakeholder groups participated in and reviewed the Value Analysis Report that describes the PRSM requirements. In addition, the Implementation Vendor has been delivering a series of Checkpoints, which include a review of the PRSM configurations and design documentation. After each checkpoint, the PRSM Project Team gathers and consolidates their feedback on what was presented and provides it to the Implementation Vendor. The Implementation Vendor originally stated that there would be four (4) checkpoints over the course of the Adaptation Phase. In the March 2010 reporting period, the implementation Vendor stated that the remainder of the configurations would be presented in Checkpoint 4 or any of number of checkpoints needed. Checkpoint 4 was performed in April 2010. The walkthrough included the review of the revised design documentation for configurations presented in previous checkpoints. Configuration requirements baseline, customizations and deleted requirement agreements were reviewed by Caltrans and feedback was provided to the Implementation Vendor. |
| Is a formal SDLC methodology followed? | X |  | The Implementation Vendor is using the SDLC Stage Gate Model to manage the configuration and customization of PRSM throughout the Adaptation Phase. In this model, work packages divide the total effort into a series of stages, where gating criteria must be met prior to moving from one stage to the next. For the PRSM Project, each work package is designed, developed, tested, and accepted prior to completion of the package. This model may have an impact on the schedule, due to the amount of review time for each work package. In order to offset this, Caltrans is incorporating review cycles through the new checkpoint implementation approach. |
| Is a software product used to assist in managing requirements? Is there tracking of requirements traceability through all life-cycle phases? | X |  | An Implementation and System Acceptance Test consultant has been added to the team. The level of requirements management presently in place appears to be appropriate for the current phase of the project. |
| Do software engineering standards exist and are they followed? | X |  | Engineering standards exist and are documented in the PRSM Configuration Management Plan. IPOC will monitor the project during the Adaptation Phase and subsequent phases to determine how effectively the PRSM Project is adhering to the engineering standards. |
| Does product defect tracking begin no later than requirements specifications? | X |  | The PRSM issue management system currently is designed to serve as a defect tracking mechanism. Several of the issues already raised represent clarification to requirements. |
| Are formal code reviews conducted? | N/A | N/A | This is not applicable for this project. However, the PRSM Project Team has planned for formal configuration reviews to occur during checkpoints throughout the Adaptation Phase. In the March 2010 reporting period, the implementation Vendor stated that the remainder of the configurations would be presented in Checkpoint 4 or any of number of checkpoints needed. Checkpoint 4 was performed in April 2010. The walkthrough included the review of the revised design documentation for configurations presented in previous checkpoints. Configuration requirements baseline, customizations and deleted requirement agreements were reviewed by Caltrans and feedback was provided to the Implementation Vendor. |
| Are formal quality assurance procedures followed consistently? | X |  | The PRSM Project follows the State Acceptance process for deliverables. There are three types of Acceptance: Acceptance Type 1 – Objective on Receipt; Acceptance Type 2 – Non-Software Acceptance; and Acceptance Type 3 – Software Acceptance Testing by the State. |
| Do users sign-off on acceptance test results before a new system or changes are put into production? | N/A | N/A | Project is in the Adaptation Phase |
| Is the enterprise architecture plan adhered to? | X |  | Caltrans is in the process of creating a formal enterprise architecture plan. The PRSM technology solution was requested to be submitted as part of the study. |
| Are formal deliverable inspections performed, beginning with requirements specifications? | X |  | An effort is underway to baseline the requirements. Although the majority of requirements are baselined, there are 3 open Project Change Requests (PCR’s) that will need to be approved before the requirements baseline effort can be completed (PCR 8, 9, and 12). In addition, the Implementation Vendor is currently in the process of mapping the requirements to the To-Be processes using the requirements tracking application RequisitePro. This traceability activity is also dependent on the approval of the 3 open PCR’s. Previously, the requirements have been through two separate review activities: user group review and IV&V review. There is a third review underway by the Project Management team in order to document the As-Is and To-Be business processes. IPOC will continue to monitor this area as the project progresses. |
| Are IV&V services obtained and used? | X |  | The IV&V Contract was approved and the IV&V Vendor began work in April 2008. |

## IPO Report for March 2010

# Independent Project Oversight Report

| Project Name: | Caltrans PRSM | Assessment Date: | Mar 31, 2010 |
| --- | --- | --- | --- |
|  | Frequency: |  |

Oversight Provider Information

| Oversight Leader: | Greg Thomas | Organization: | Deloitte & Touche LLP |
| --- | --- | --- | --- |
| Phone Number: | 916 288 3232 | Email: | grethomas@deloitte.com |

Project Information

| Project Number: | 2660-160 | Department: | Transportation (Caltrans) |
| --- | --- | --- | --- |
| Criticality: | High | Agency: | Business, Transportation & Housing |
| Last Approved Document/Date: | SPR (12/08/09) | Total One-time Cost: | $26,078,375 |
| Start Date: | June 7, 2000 | End Date: | June 13, 2011 |
| Project Manager: | David Youmans | Organization: | Caltrans |
| Phone Number: | 916.826.4425 | Email: | david_youmans@dot.ca.gov |

Summary: Current Status

| Project Phase: | Adaptation |
| --- | --- |
| Planned Start Date: | May 20, 2009 | Planned End Date: | February 2, 2010 |
| Actual Start Date: | July 1, 2009 | Forecasted End Date: June 29, 2010 |

Schedule

Select the statement that most closely applies, measured against the last Finance approved document.

| Behind Schedule | Ahead-of-schedule: One or more major tasks or milestones have been completed and approved early (> 5%). All other major tasks and milestones completed and approved according to plan. On-schedule: All major tasks and milestones have been completed and approved according to plan. (Within 5%) Behind Schedule: One or more major tasks or milestones are expected to be delayed. (> 5%) |
| --- | --- |
| Comments: | A new baseline schedule was set with the approved SPR dated December 8, 2009. The SPR states the end date of the Adaptation Phase as February 2010. In the March 2, 2010 PRSM Project status meeting, the Implementation Vendor identified the Adaptation Phase completion date as June 29, 2010. For the Adaptation Phase, this represents a difference of four (4) months or approximately a 57% delay. Additionally, the SPR states the end date of the entire PRSM project as June 13, 2011. In the March 2, 2010 PRSM Project Status meeting, the Implementation Vendor identified the PRSM Project completion date as October 10, 2011. This represents an extension of the project by four (4) months or approximately a 15% delay. Given this change, IPOC has reported the project as “Behind Schedule”. Please note that the PRSM Project Team is still in the process of determining the overall timeline for the project. While the end of the Adaptation Phase milestone is behind schedule by 4 months it is possible that the project will complete on time (by June 13, 2011). Efforts by the PRSM Project Team, such as concurrent configuration of agreed upon requirements, are currently underway to offset some of the delay in Adaptation. We will continue to closely monitor the schedule status during the Adaptation Phase and report any updates as they occur. Please see the risks section below for information regarding further potential impact to the schedule. |

Resources (Level of Effort) Choose the statement that most closely applies.

| Within Resources | Fewer Resources Completion of one or more major tasks and/or acceptable products has required or is expected to require materially (>5%) fewer hours/staff than planned. Within Resources All major tasks have been completed and acceptable products created using the planned number of hours/staff (within 5%). More Resources Completion of major tasks and/or acceptable products has required or is expected to require materially (>5%) more hours/staff than planned. |
| --- | --- |
| Comments: | A new baseline was set with the approved SPR dated 12/08/2009. |

Resources (Budget/Cost) Choose the statement that most closely applies.

| Within Cost | Less cost The project is (>5%) under budget. Within cost The project is operating within budget. Higher cost Material budget increases (>5%) are likely. |
| --- | --- |
| Comments: | A new baseline was set with the approved SPR dated 12/08/2009. |

Quality (Client Functionality) Choose the statement that most closely applies.

|  | Adequately Defined Required client functionality is adequately defined, and is being successfully built into the system, given the current project phase. Inadequately Defined One or more significant components of required client functionality are inadequately defined, or are not being successfully built into the system, given the current project phase. |
| --- | --- |
| Comments: | Functionality is adequately defined for the Adaptation Phase which began on July 1, 2009. In February 2010, the Implementation Vendor delivered the third checkpoint review, which included the review of the revised design documentation for configurations presented in previous checkpoints. Configuration requirements baseline, customizations and deleted requirement agreements were reviewed by Caltrans and feedback was provided to the Implementation Vendor. The PRSM Project Team has been made aware that Caltrans Financial Data to Oracle (FIDO) system and Earned Value Reporting System (EVRS) are going to be phased out once the ERP Financial Infrastructure (EFIS) has been implemented. Based on this information, the PRSM Project Team has created PCR 13, which involves building an interface to EFIS. PCR 13 is currently under analysis (analysis activities include requirements identification). In addition, there are currently 3 open Project Change Requests (PCR’s) that include changes and/or deletions to existing requirements / functionality (PCR 8, 9, and 12). The majority of these changes involve interface requirements. The PRSM Change Management Team has placed these PCR’s on hold until PCR 13 has been approved. |

Quality (Architecture/System Performance) Choose the statement that most closely applies.

|  | Adequately Defined The system technical architecture is adequately defined, and modeling, benchmarking and testing are being conducted (or are planned) appropriate to the current project phase. Inadequately Defined The system technical architecture is not adequately defined, or modeling, benchmarking and testing are not being conducted (or are planned) appropriate to the current project phase. |
| --- | --- |
| Comments: | System technical architecture and performance are adequately defined for the Adaptation Phase. The Implementation Vendor has submitted a Configuration Management Plan, High Level Design, and updated Architecture Diagram. The Production environment hardware has been configured and turned over to Caltrans. The software applications are currently being installed and tested. The previous issue with the development environment has been resolved. |

Issues

Issue Title: EFIS Interface

Issue Statement: The PRSM Project Team has been made aware that Caltrans Financial Data to Oracle (FIDO) system and Earned Value Reporting System (EVRS) are going to be phased out once the ERP Financial Infrastructure (EFIS) has been implemented.  While developing to one standard interface presents a business opportunity, specifications and data requirements will need to be analyzed and documented.  The development of the EFIS interface is a critical step for the PRSM project to proceed to the Pilot phase.  Currently EFIS is scheduled to go-live in July 2010 and PRSM is scheduled to begin Pilot on 6/28/2010.  A delay in the EFIS schedule could significantly delay the PRSM pilot and roll out to the Districts.   In addition, the development of the EFIS interface could impact the cost of PRSM.  There are three (3) potential scenarios related to this issue that could impact the schedule and/or cost: 1) a delay in the EFIS project could result in a delay to PRSM; 2) the complexity of the interface to EFIS and the activities/tasks involved could result in a delay to PRSM and/or impact cost; and 3) a delay in the EFIS training schedule could conflict with the PRSM training schedule, which could result in a delay to PRSM.

Impact: High	Time Frame:  Short Term	Severity:  High	Assigned to: Jacqueline Moore

Recommendations:

- Develop a detailed action plan for the EFIS interface that addresses the following: impact to the data conversion effort, impact to districts and end users, impact to project resources, impact to schedule, and impact to costs.

- Update the PRSM project schedule with the activities associated with the EFIS interface, including analysis activities.

- Continue to work closely with the EFIS project by attending the bi-weekly interface planning meetings.  Escalate issues related to EFIS timing and resource needs to the PRSM Steering Committee for resolution as soon as the interface requirements are finalized.

Status Update:

Mar 10 Status:	An impact analysis is currently being performed for the EFIS interface change request (PCR 13).  The PRSM Project Team continues to meet with the EFIS Project Team on a weekly basis.  According to the PRSM Project Schedule dated March 23, 2010, EFIS data conversion activities are scheduled to be completed in May 2010.

Feb 10 Status:	The PRSM Project Team has been performing analysis activities for the EFIS interface during the month of February.  The EFIS and PRSM Project Teams have been meeting on a weekly basis to discuss the EFIS project and its interface to PRSM.  In addition three (3) EFIS risks have been added to the PRSM Risk Log, risks 76A, 76B, and 77.  These risks are discussed during the monthly PRSM Risk Management meeting.  The next PRSM Risk Management meeting is scheduled for March 3rd.  The PRSM Project Team has created Project Change Request (PCR) 13 for the EFIS Interface effort.  PCR 13 is currently under analysis.

New Risks

No new risks

Progress Toward Addressing Prior Risks

Risk Title: PRSM Task Dependency Identification

Risk Statement: Recent activities to refresh/reevaluate the schedule have resulted in a significant number of previous unknown dependencies between interface development activities, configuration activities, and data conversion activities.  The identification of these could result in further delay to the overall project schedule.

Probability:  High        Impact: High     Time Frame:  Long Term	   Severity:  High	       Assigned to: David Youmans

Recommendation:

- During the weekly PRSM Project Status meetings, IPOC recommends that each of the Caltrans PRSM Project Team Workgroups conduct brief and more frequent status meetings regarding status of tasks, dependencies, risks and issues associated with those tasks.  In addition, IPOC recommends that the PRSM Project Team continues to refine the schedule for project phases after Adaptation to ensure that any risk of further schedule slippage is mitigated and so that the total impact of known dependencies on the schedule can be understood and communicated to stakeholders.

Status Update:

Mar 10 Status:	No new status

Feb 10 Status:	The PRSM Project Team has continued to reevaluate the PRSM Project Schedule during the month of December.  During the weekly PRSM Project Status meetings, current and up-coming tasks are discussed and risks and dependencies associated with those tasks are identified.  For a status update on the requirements baselining process, please refer to Risk: Business Rules and Business Process Changes below.

Risk Title: PRSM Project Team Communications

Risk Statement: Effective, clear and frequent communications between the Caltrans PRSM team, the Implementation Vendor, other vendors (e.g., testing and data conversion), and District stakeholder is critical given the size and complexity of PRSM during the Adaptation Phase.  The new Communications Plan, while documented, needs to be fully implemented early in the Adaptation Phase.  Without effective communications, the PRSM project schedule, scope and quality could be difficult to manage and control.

Probability:  Medium        Impact: High     Time Frame:  Long Term	 Severity:  High	    Assigned to: David Youmans

Recommendation:

- In addition to the weekly PRSM Project Status meetings, IPOC recommends that Caltrans PRSM Project Management and Implementation Vendor Project Management conduct frequent status meetings in order to discuss the status of high priority issues and action items.  These checkpoint meetings should be no longer than ½ hour in duration and conducted twice per week (i.e., Monday AM and Thursday PM).

- Expedite the communication of the detailed To-Be Business Process changes to the Districts so that they can gain a better understanding of the impacts and benefits of PRSM.

Status Update:

Mar 10 Status:	Previously, the PRSM Project Team was going to create Whitepapers and multi-media Trailers to provide additional information to the districts regarding PRSM To Be processes.  Due to the compressed timeframe and resource constraints, the PRSM Project Team has decided to focus their efforts on producing the Trailers, instead of the Whitepapers.  Activities associated to the Trailer development has been added to the PRSM project schedule.  Currently the owner of this activity is identifying resources to assist with this effort.

Feb 10 Status:	Beginning in January 2010, project risks have been added as a discussion point during the weekly PRSM project status meetings.  During this discussion, a select number of risks are discussed, including their current status, impact, and remediation steps.  The Communications Plan was formally approved in the month of August and provides details surrounding the methods of communication for the PRSM project.  PRSM Project Status meetings continue to occur on a weekly basis.  PRSM sub-teams meet at a minimum of once a week to discuss current and upcoming tasks.  In addition to the PRSM Project Team meetings, Caltrans prepares and distributes a monthly newsletter and “Nuggets of Knowledge” memo to the districts.  Implementation Team training sessions have been scheduled during the month of September that will provide the PRSM Implementation Team with an overview of PRSM Methodology and Functionality.  The PRSM Project Team has identified the need to establish and document Marketing activities in order to provide Districts will more detailed information regarding PRSM features.  Currently this task has been assigned to an owner, who is in the process of identifying the detailed tasks associated with this effort and incorporating them into the PRSM schedule.

Risk Title: Resource Availability

Risk Statement:  Without adequate Caltrans resources working on PRSM, the project implementation schedule could be delayed.  While in the Adaptation Phase, PRSM Project Team members should be allocated full time.  Individual Resources may need to be identified at the task level in the Project Plan in order to estimate resource requirements and availability.

Probability:  Medium	Impact: High 		Time Frame:  Short  	Severity:  High	Assigned to: TBD

Recommendations:

- After the PRSM work plan is complete, determine the resource gaps and reallocate effort as appropriate.

- Assign individual resources at the task level in the project schedule to assist in estimating resource requirements.  All PRSM project resources, including vendor resources, should be included.

Status Update:

Mar 10 Status:	No new status

Feb 10 Status:	During the September 09 reporting period, a CA Clarity technical resource was unavailable during the business objects migration to virtual environments.  This resulted in a delay of the business object migration task.

Risk Title:  Business Rules and Business Process Changes

Risk Statement: The impact of business changes resulting from the PRSM implementation needs to be sufficiently understood, planned for, and communicated to Caltrans staff.  If District field staff are not in agreement with the decisions and consequences of changing/standardizing business rules and business processes, it may have an adverse effect on system acceptance and may disrupt work in progress.  This could result in increased resistance to acceptance and usage of the system.

Probability:  High 	    Impact:  High 	   Time Frame:  Med 	  Severity:  High	Assigned to: David Cordone

Recommendations:

- Implement a formal change management process which will be used for PRSM project related changes.  Change management tasks associated with these changes should be incorporated into the project schedule and budget.  Changes should be communicated to the key stakeholders.

- Define the process for gaining field consensus on the new business rules and business processes.

- Develop a plan that describes how information on new business rules and business processes will be communicated to the field with sufficient time to get feedback and buy-in.

- Expedite the communication of the detailed To-Be Business Process changes to the Districts so that they can gain a better understanding of the impacts and benefits of PRSM.

Status Update:

Mar10 Status:	An effort is underway to baseline the PRSM requirements.  In addition, the Implementation Vendor is currently in the process of mapping the requirements to the To-Be processes using the requirements tracking application RequisitePro.  Both activities are dependent on the approval of the 3 open Project Change Requests (PCR 8, 9, and 12).

Feb10 Status:	There are currently 3 open Project Change Requests (PCR’s) that include changes and/or deletions to existing requirements / functionality (PCR 8, 9, and 12).  The majority of these changes involve interface requirements.  The PRSM Change Management Team has placed these PCR’s on hold until PCR 13 (Developing an Interface to EFIS) has been approved.

General Comments

Deloitte & Touche LLP’s IPOC contract with the Caltrans PRSM project started in December 2008.  This Independent Project Oversight Report (IPOR) provided by Deloitte & Touche LLP has been developed in accordance with the applicable standards of the American Institute of Certified Public Accountants (AICPA) as per Deloitte & Touche LLP policy.  IPOC has attended various PRSM project meetings throughout the month of March, including PRSM Status meetings, PRSM Change Management meetings, the PRSM Implementation Managers meeting, PRSM Risk Management meeting, and the PRSM Advisory Committee meeting.

The PRSM project is in the Adaptation Part B Phase of the project.  Five deliverables have been identified to be completed during the Adaptation Phase: Application Installation Report, Data Initialization Plan, Training Role Descriptions and Course List, Training and Documentation Plan and Pilot Plan.  IPOC is planning to review each of these deliverables as they are submitted and will provide comments and feedback.

PRSM project status meetings occur on a weekly basis.  During the status meetings, the Implementation Vendor distributes an updated status report, which includes an updated schedule in Microsoft Project for the current phase.  The schedule provides a detailed view of the status of activities, deliverables, and milestones.  The status report also includes a Past Due Task Status Register and an Action Item / Decision Register.  In addition, PRSM Change Management meetings occur on a weekly basis following the PRSM status meeting.  During these meetings new and open project change requests (PCR’s) are discussed by PRSM Project Management and the Implementation Vendor Project Manager.

The Implementation Vendor has submitted an Adaptation Phase schedule to Caltrans, which separates the Adaptation Phase into two parts (A and B).  In addition, the Implementation Plan was submitted, which was reviewed by Caltrans, and includes a schedule for the entire project.  The Implementation Vendor is using a Rolling Wave scheduling process for the PRSM project where a more detailed schedule is prepared before the start of each project phase.  Prior to the end of each phase or PRSM Payment Point, the Implementation Vendor and Caltrans will work together to develop the specific activities for the tasks in the next Rolling Wave.  In October 2009, the Implementation Vendor proposed a new implementation approach to replace the iterative work package approach.   This new approach involves establishing a series of checkpoints throughout the remainder of the Adaptation Phase.  During each checkpoint, configured or customized functionality is reviewed by the PRSM Project Team through meetings facilitated by the Implementation Vendor.  In February 2010, the Implementation Vendor delivered the third checkpoint review, which included the review of the revised design documentation for configurations presented in previous checkpoints.  Checkpoint 4 is scheduled to occur on April 5th and 6th.

In addition to the new implementation approach, recent activities to refresh/reevaluate the schedule have resulted in a significant number of previous unknown dependencies between interface development activities, configuration activities, and data conversion activities.  As a result of this, the PRSM Project Team tasked the individual PRSM workgroups (i.e. Training Team, Configuration Team, etc…) with break down the tasks for their group and identifying tasks and dependencies.  On October 20, 2009 the PRSM Project Team held a PRSM Schedule Review Meeting with all of the workgroups, where the updated tasks and dependencies for each workgroup where presented to the entire PRSM Project Team.   Based on the output of this session, an updated schedule was produced which includes the updated tasks, dependencies, and resources.  This updated schedule is scheduled to be finalized in January and will include resource loading.  Project Change Requests (PCR’s) have been created for changes to and/or deletions of PRSM requirements.  There are currently 3 open Project Change Requests (PCR’s) that include changes and/or deletions to existing requirements / functionality (PCR 8, 9, and 12).  The majority of these changes involve interface requirements.  The PRSM Change Management Team has placed these PCR’s on hold until PCR 13 (Developing an Interface to EFIS) has been approved.

Production equipment has been procured and is onsite being configured.  The training and testing environments have been implemented and business objects have been installed in those environments.  The previous issue with the development environment has been resolved.

A new baseline schedule was set with the approved SPR dated December 8, 2009.  The SPR states the end date of the Adaptation Phase as February 2010.  In the March 2, 2010 PRSM Project status meeting, the Implementation Vendor identified the Adaptation Phase completion date as June 29, 2010.  For the Adaptation Phase, this represents a difference of four (4) months.  Additionally, the SPR states the end date of the entire PRSM project as June 13, 2011.  In the March 2, 2010 PRSM Project Status meeting, the Implementation Vendor identified the PRSM Project completion date as October 10, 2011.  This represents an extension of the project by four (4) months.  Given this change in the end date, IPOC has reported the project as “Behind Schedule”.  For more information, please refer to the Schedule section of Page 1 of this IPOR.

## Project Oversight Review Checklist for March 2010

Project Oversight Review Checklist: High Criticality Project

This checklist is an assessment for the Adaptation Phase. The end date of this phase is June 2010.

| Practices and Products | Adequate | Deficient | Notes: Items Reviewed; Interviews Conducted; Demonstration |
| --- | --- | --- | --- |
| Planning and Tracking |
| Have the business case, project goals, objectives, expected outcomes, key stakeholders, and sponsor(s) identified and documented? | X |  | An updated SPR was approved by the OCIO on December 8, 2009. The appropriate project documents, including the PRSM Project Schedule, should be updated with the new information from the SPR. |
| Has a detailed project plan with all activities (tasks), milestones, dates, and estimated hours by task loaded into project management (PM) software? Are the lowest level tasks of a short duration with measurable outcomes? | X |  | The Implementation Vendor submitted a PRSM Project Implementation Plan during the Planning Phase of the project. The Implementation Plan provides a schedule in MS Project for project activities, milestones, and deliverables including start and finish dates, duration, and high level resource assignments for each task. The Implementation Vendor is using a Rolling Wave scheduling approach. Prior to the end of each phase or PRSM Payment Point, the Implementation Vendor and Caltrans work together to develop the specific activities for the tasks in the next Rolling Wave. The new detailed Rolling Wave Plan for the succeeding Project Phase will be documented in MS Project and will be submitted for State Acceptance as a prerequisite for State Acceptance of the current Payment Point. In October 2009, the Implementation Vendor proposed a new implementation approach to replace the iterative work packages. This new approach involves establishing a series of checkpoints throughout the remainder of the Adaptation Phase. During each checkpoint, configured or customized functionality is reviewed by the PRSM Project Team through meetings facilitated by the Implementation Vendor. In February 2010, the Implementation Vendor delivered the third checkpoint review, which included the review of the revised design documentation for configurations presented in previous checkpoints. Checkpoint 4 is scheduled to occur on April 5th and 6th. Configuration requirements baseline, customizations and deleted requirement agreements were reviewed by Caltrans and feedback was provided to the Implementation Vendor. Finalization of interface and conversion requirements has been delayed until the completion of Project Change Request (PCR) 13, which is the change request for the ERP Financial Infrastructure (EFIS) interface. Rolling Wave Two was closed out and RW 2 activities not completed were moved to Rolling Wave 3. Rolling Wave 3 activities include completing configurations, developing interfaces and conversion processes, testing configurations and interfaces, and developing the training materials. Activities to reevaluate the schedule have resulted in a significant number of previous unknown dependencies between interface development activities, configuration activities, and data conversion activities. As a result of this, the PRSM Project Team tasked the PRSM workgroups (i.e. Training Team, Configuration Team, etc…) with breaking down the tasks for their group and identifying tasks and dependencies. On October 20, 2009 the PRSM Project Team held a PRSM Schedule Review Meeting with the workgroups, where the updated tasks and dependencies for each workgroup where presented to the entire PRSM Project Team. Based on the output of this session, an updated schedule was produced which included the updated tasks, dependencies, and resources. |
| Is completion of planned tasks recorded within the PM software? | X |  | In October 2009, the Implementation Vendor proposed a new implementation approach to replace the iterative work packages. This new approach involves establishing a series of checkpoints throughout the remainder of the Adaptation Phase. During each checkpoint, configured or customized functionality is reviewed by the PRSM Project Team through meetings facilitated by the Implementation Vendor. Activities to reevaluate the schedule have resulted in a significant number of previous unknown dependencies between interface development activities, configuration activities, and data conversion activities. As a result of this, the PRSM Project Team tasked the individual PRSM workgroups (i.e. Training Team, Configuration Team, etc…) with breaking down the tasks for their group and identifying tasks and dependencies. On October 20, 2009 the PRSM Project Team held a PRSM Schedule Review Meeting with the workgroups, where the updated tasks and dependencies for each workgroup where presented to the PRSM Project Team. Based on the output of this session, an updated schedule was produced which included the updated tasks, dependencies, and resources. |
| Are actual hours expended by task recorded at least monthly within PM software? | X |  | Actual hours are charged to a WBS and are recorded and tracked in the Department’s official accounting system. An overall project WBS list of approximately 2,000 items exists in MS Excel. |
| Are estimated hours to complete by task recorded at least monthly within PM software? | X |  | Activities to reevaluate the schedule have resulted in a significant number of previous unknown dependencies between interface development activities, configuration activities, and data conversion activities. As a result of this, the PRSM Project Team tasked the PRSM workgroups (i.e. Training Team, Configuration Team,) with breaking down the tasks for their group and identifying tasks and dependencies. On October 20, 2009 the PRSM Project Team held a PRSM Schedule Review Meeting with the workgroups, where the updated tasks and dependencies for each workgroup where presented to the PRSM Project Team. Based on the output of this session, a revised schedule was produced which included the updated tasks, dependencies, and resources. On a weekly basis, current and upcoming tasks are reviewed by the PRSM Project team and the estimated hours to complete the tasks are updated as necessary. |
| Is there a formal staffing plan, including a current organization chart, written roles and responsibilities, plans for staff acquisition, schedule for arrival and departure of specific staff, and staff training plans | X |  | Formal staffing plans, including a current organization chart and written roles and responsibilities exist for the Caltrans PRSM Project Team and the Implementation Vendor. |
| Have project cost estimates, with supporting data for each cost category, been maintained? | X |  | The latest approved SPR dated December 8, 2009 has reset the baseline. |
| Are software size estimates developed and tracked? | N/A | N/A | This item is not applicable. |
| Are two or more estimation approaches used to refine estimates? | N/A | N/A | This item is not applicable. |
| Are independent reviews of estimates conducted? | N/A | N/A | This item is not applicable. |
| Are actual costs recorded and regularly compared to budgeted costs? | X |  | A spreadsheet exists that shows planned and actual costs by month. |
| Is supporting data maintained for actual costs? | X |  | Actual costs are obtained from timesheets that allocate time to WBS numbers/tasks. |
| Is completion status of work plan activities, deliverables, and milestones recorded, compared to schedule and included in a written status reporting process? | X |  | Beginning in the May 2009 reporting period, PRSM project status meetings have been occurring on a weekly basis versus bi-weekly. During the meetings, the Implementation Vendor distributes an updated status report, which includes an updated schedule in MS Project for the current phase. The schedule provides a detailed view of the status of activities, deliverables, and milestones for the current phase. In addition, the status report also includes a Past Due Task Status Register and an Action Item / Decision Register. A high-level status report is posted on the Caltrans Improvement Project web database. Status reports go to the Legislature quarterly. |
| Are key specification documents (e.g. contracts, requirement specifications and/or contract deliverables) and software products under formal configuration control, with items to be controlled and specific staff roles and responsibilities for configuration management identified in a configuration management plan? | X |  | The Configuration Management Plan deliverable was submitted by the Implementation Vendor to Caltrans during the Planning Phase. After Caltrans and IPOC performed an initial review of the Plan, the Implementation Vendor submitted an updated version. The current Configuration Management Plan, dated 7/19/2009, provides details on configuration management of key project documents and software products. |
| Are issues/problems and their resolution (including assignment of specific staff responsibility for issue resolution and specific deadlines for completion of resolution activities), formally tracked? | X |  | An Issue Management Plan was approved and open issues are in the project database. The IT project manager is considering the same tool for managing project changes. Additionally, Caltrans has established an Issues Management Meeting that is held on a monthly basis. |
| Is user satisfaction assessed at key project milestones? | X |  | Representatives of the engineering areas and regions participated in the vendor demonstration evaluations. In addition, Caltrans scheduled Implementation Team training sessions that provided the PRSM Implementation Team with an overview of PRSM Methodology and Functionality. Training Session #1 occurred during the week of September 14th. After completion of Session #1 training, the PRSM Project Team gathered feedback on the content and the effectiveness of the training and used the feedback to update and/or improve Training Session #2, which occurred during the week of September 28th. This is adequate for the Adaptation Phase of the project. |
| Is planning in compliance with formal standards or a system development life-cycle (SDLC) methodology? | X |  | Compliance with PMBOK standards is adequate for this phase of the project. Five deliverables have been identified to be completed during the Adaptation Phase: Application Installation Report, Data Initialization Plan, Training Role Descriptions and Course List, Training and Documentation Plan and Pilot Plan. IPOC is planning to review each of these deliverables as they are submitted and will provide comments and feedback. |
| Is there formal enterprise architecture in place? | X |  | The RFQI describes the target Caltrans enterprise environment. |
| Are project closeout activities performed, including a PIER, collection and archiving up-to-date project records and identification of lessons learned? | N/A | N/A | Project is in the Adaptation Phase. |
| Procurement |
| Are appropriate procurement vehicles selected (e.g. CMAS, MSA, “alternative procurement”) and their required processes followed? | X |  | The final contract was signed by the Implementation Vendor on February 26, 2009. Caltrans received, reviewed and signed the contract on February 27, 2009. DGS Legal reviewed and signed the contract on March 5th, 2009. |
| Is a detailed written scope of work for all services included in solicitation documents? | X |  | Detailed written scope of work is contained in the RFP. |
| Are detailed requirement specifications included in solicitation documents? | X |  | Detailed requirement specifications are contained in the RFP. Requirements are described in the RFQI and Value Analysis documents. |
| Is there material participation of outside expertise (e.g. DGS, Departmental specialists, consultants) in procurement planning and execution? | X |  | Outside expertise and counsel has been sought from DOF, DGS, and consultants. |
| For large-scale outsourcing, is qualified legal counsel obtained? | N/A | N/A | The project does not involve outsourcing as currently defined. |
| Risk Management |
| Is formal continuous risk management performed, including development of a written risk management plan, identification, analysis, mitigation and escalation of risks in accordance with DOF/TOSU Guidelines, and regular management team review of risks and mitigation progress performed? | X |  | The latest version of the Risk Management Plan was submitted April 30, 2009. Risk owners have been assigned. A Risk Register was developed and is tracked by the Risk Manager. |
| Does the management team review risks and mitigation progress at least monthly? | X |  | Risk Management meetings are being held monthly with the PRSM Project Team where risks and their associated mitigation progress are reviewed. |
| Are externally developed risk identification aids used, such as the SEI Taxonomy Based Questionnaire? | X |  | A risk list was initially populated using the SEI Risk Taxonomy. Additional risks are added to the list migration from the issue list. |
| Communication |
| Is there a written project communications plan? | X |  | The latest version of the finalized and approved Communications Plan is dated 6/22/2009. |
| Are regular written status reports prepared and provided to the project manager, department CIO (if applicable) and other key stakeholders? | X |  | The Advisory Committee receives a written status report during the monthly Advisory Committee meetings. These reports include issues identified, changes to scope, schedule, cost, problems encountered, and items accomplished. |
| Are there written escalation policies for issues and risks? | X |  | Both the Risk Management Plan and the Issue Management Plan contain a risk escalation process. |
| Is there regular stakeholder involvement in major project decisions, issue resolution and risk mitigation? | X |  | Implementation Manager meetings occur on a monthly basis. The purpose of this meeting is to keep the District project managers regularly updated on the status of the project and to receive their input. |
| System Engineering |
| Are users involved throughout the project, especially in requirements specification and testing? | X |  | Representatives of key stakeholder groups participated in and reviewed the Value Analysis Report that describes the PRSM requirements. The PRSM Project Team is being run by Caltrans Division of Project management which is the primary constituency for the system. |
| Do users formally approve/sign-off on written specifications? | X |  | The PRSM Advisory Committee is comprised of Caltrans personnel. The Advisory Committee appears to be monitoring the initial planning process. This level of involvement appears to be appropriate for the current phase of the project. |
| Is a formal SDLC methodology followed? | X |  | The Implementation Vendor is using the SDLC Stage Gate Model to manage the configuration and customization of PRSM throughout the Adaptation Phase. In this model, work packages divide the total effort into a series of stages, where gating criteria must be met prior to moving from one stage to the next. For the PRSM Project, each work package is designed, developed, tested, and accepted prior to completion of the package. This model may have an impact on the schedule, due to the amount of review time for each work package. In order to offset this, Caltrans is incorporating review cycles through the new checkpoint implementation approach. |
| Is a software product used to assist in managing requirements? Is there tracking of requirements traceability through all life-cycle phases? | X |  | An Implementation and System Acceptance Test consultant has been added to the team. The level of requirements management presently in place appears to be appropriate for the current phase of the project. |
| Do software engineering standards exist and are they followed? | X |  | Engineering standards exist and are documented in the PRSM Configuration Management Plan. IPOC will monitor the project during the Adaptation Phase and subsequent phases to determine how effectively the PRSM Project is adhering to the engineering standards. |
| Does product defect tracking begin no later than requirements specifications? | X |  | The PRSM issue management system currently is designed to serve as a defect tracking mechanism. Several of the issues already raised represent clarification to requirements. |
| Are formal code reviews conducted? | N/A | N/A | This is not applicable for this project. However, the PRSM Project Team has planned for formal configuration reviews to occur during checkpoints throughout the Adaptation Phase. In February 2010, the Implementation Vendor delivered the third checkpoint review, which included the review of the revised design documentation for configurations presented in previous checkpoints. Checkpoint 4 is scheduled to occur April 5th and 6th. |
| Are formal quality assurance procedures followed consistently? | X |  | The PRSM Project follows the State Acceptance process for deliverables. There are three types of Acceptance: Acceptance Type 1 – Objective on Receipt; Acceptance Type 2 – Non-Software Acceptance; and Acceptance Type 3 – Software Acceptance Testing by the State. |
| Do users sign-off on acceptance test results before a new system or changes are put into production? | N/A | N/A | Project is in the Adaptation Phase |
| Is the enterprise architecture plan adhered to? | X |  | Caltrans is in the process of creating a formal enterprise architecture plan. The PRSM technology solution was requested to be submitted as part of the study. |
| Are formal deliverable inspections performed, beginning with requirements specifications? | X |  | An effort is underway to baseline the requirements. Although the majority of requirements are baselined, there are 3 open Project Change Requests (PCR’s) that will need to be approved before the requirements baseline effort can be completed (PCR 8, 9, and 12). In addition, the Implementation Vendor is currently in the process of mapping the requirements to the To-Be processes using the requirements tracking application RequisitePro. This traceability activity is also dependent on the approval of the 3 open PCR’s. Previously, the requirements have been through two separate review activities: user group review and IV&V review. There is a third review underway by the Project Management team in order to document the As-Is and To-Be business processes. IPOC will continue to monitor this area as the project progresses. |
| Are IV&V services obtained and used? | X |  | The IV&V Contract was approved and the IV&V Vendor began work in April 2008. |